## WRDWP Data Input
General Identifying Information | [16 empty] | Waterbody, RWSP, and MFL Benefited | [5 empty] | Water Made Available | [5 empty] | 5-Year Water Resource Development Work Program | [8 empty] | General Funding | [11 empty] | Comments
DEP Unique ID | Water Management District | Year First Added to RWSP/RPS | District Project Number | Phased or Linked Project | Associated District Project Number | Project Name | Cooperating Entity | Lat | Long | Project Type | Land Acquisition Component | Project Description | Short Description | Project Status | Construction Beginning Date | Construction Completion Date | Waterbody Benefited | RWSP Region Supported | RWSP or RPS Year Project Last Identified | Primary MFL Supported | Ancillary MFL Supported | MFL RPS Supported, if applicable | Quantity of Water Made Available to date (MGD) | Quantity of Water Made Available upon Completion (MGD) | Reuse Flow Made Available to date (MGD) | Reuse Flow Made Available upon Project Completion (MGD) | Storage Capacity Created (MG) | Distribution / Transmission Capacity Created (MGD) | Fiscal Year Included in 5-Year WRDWP, If Applicable | Historic District Expenditures | WRDWP Current FY Funding | WRDWP Current FY+1 Funding | WRDWP Current FY+2 Funding | WRDWP Current FY+3 Funding | WRDWP Current FY+4 Funding | Budget Reference | WRD or WSD (optional) | Projected Total Funding (for RWSP/RPS Options Only) | Initial fiscal year funded | Most recent fiscal year funded | WPSP Funding | Springs Funding | Other state funding | Total State Funding | Total District Funding | Total Land Acquisition Funding by District or State | Cooperating Entity Match | Total Construction Costs | Project Total | Comments | Explanation for 5-Year WRDWP
| SWFWMD | 2020 | B015 |  |  | Water Incentives Supporting Efficient (WISE) Program | TBD | 28.4698 | -82.443 | PS and ICI Conservation | No | The Water Incentives Supporting Efficiency (WISE) program is a cost reimbursement program that supports the implementation of water conservation projects by non agricultural water users. This will assist in meeting the District's strategic goals associated with increased water use efficiency. The program provides 50 percent of eligible project costs up to $20,000 of District funds per project. Potential applicants include, but is not limited to, hospitals, schools, prisons, Homeowners Association irrigation, golf courses, hotels, manufacturing, food processing facilities, other commercial properties and small utilities. Applications are accepted year round, and funds are allocated on a first come, first served basis. This program began in FY2019 as a follow up to the District Water Conservation Initiative. | Administer a cost reimbursement program to promote the implementation of water conservation projects by providing grants to non-agricultural water users. | Construction/Underway | 2019-10-01 | NA | SWUCA Water Bodies NTBWUCA Water Bodies DPCWUCA Water Bodies | SWF District-wide | 2020 | N/A |  |  | 0.297 | 0.652 | 0 | 0 | 0 | 0 | FY2018-19 through FY2025-26 | 477983 | 225000 | 225000 | 225000 | 225000 | 225000 | 2.2.2.7 - Conservation Rebates and Retrofits | WSD | NA | FY2019 | FY2026 | 0 | 0 | 0 | 0 | Annual Request | 0 | 0 |  | Annual Request |  |  | 1
| SWFWMD | 2006 | H017 |  |  | Facilitating Agricultural Resource Management Systems (FARMS) Program | TBD | 27.3376 | -82.4352 | Agricultural Conservation | No | The annual request for FARMS project funding supports many site-specific projects that employ agricultural BMPs to reduce groundwater withdrawals and increase the water use efficiency of agricultural operations. Over 262 projects have been approved and a cumulative 33 mgd of groundwater offsets have been achieved. In conjunction with water supply BMPs, water quality and natural systems improvement BMPs also may be cost-shared in priority areas. The projects are public/private partnerships where the District provides financial incentives to farmers to increase the water use efficiency of their operations. Reimbursement can amount to as much as 50 percent with water quality or groundwater quantity savings/conservation BMPs, or 75 percent if both quality and quantity benefits are achieved. Each project’s performance is tracked for 5 to 10 years to determine its effectiveness toward program goals. | Implement the FARMS initiative throughout the Southwest Florida Water Management District, where public/private partnerships incentize farmers to increase the water use efficiency of their operations. | Construction/Underway | 2005-10-01 | NA | SWUCA Water Bodies NTBWUCA Water Bodies DPCWUCA Water Bodies Shell Creek Prairie Creek Joshua Creek Horse Creek | SWF District-wide | 2020 | N/A |  | Southern WUCA | 26.7 | 33.6 | 0 | 0 | 0 | 0 | FY2018-19 through FY2025-26 | Annual Request | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 2.2.1.2 - Facilitating Agricultural Resource Management Systems | WRD | 0 | >FY2005 | FY2025 | 0 | 0 | 0 | 0 | Annual Request | 0 | 0 | 0 | Annual Request |  |  | 2
| SWFWMD | 2010 | H089 | Linked | P189 | MIA Recharge SWIMAL Recovery at Flatford Swamp | SWFWMD | 27.3929 | -82.1504 | Groundwater Recharge | No | Hydrologic alterations and excess runoff have adversely impacted the Flatford Swamp in the upper Myakka watershed. The District has conducted evaluations to explore potential beneficial uses of water. In 2016, evaluations began on an injection recharge option that would use excess flow affecting the swamp to recharge the Upper Floridan aquifer in the vicinity of the MIA of the SWUCA to slow saltwater intrusion. The recharge system would assist with the SWUCA Recovery Strategy’s goal of meeting the SWIMAL to help recover and protect groundwater resources in/near the MIA. The ongoing evaluation includes construction of test recharge wells in the Flatford Swamp and the design and permitting of diversion infrastructure for source water. | Evaluations that would use excess flow to recharge the Upper Floridan to slow saltwater intrusion. The project includes construction of diversion infrastructure for the excess water and recharge testing. | Construction/Underway | 2017-10-01 | 2023-12-31 | SWUCA Water Bodies Upper Myakka River | SWF Southern | 2015 | SWUCA SWIMAL |  | Southern WUCA | 0 | 2 | 0 | 0 | 0 | 0 | FY2010, FY2018-19 through FY2025-26 | 6153890 | 0 | 0 | 0 | 0 | 0 | 2.2.1.3 - Minimum Flows and Minimum Water Levels Recovery | WRD |  | FY2010 | FY2021 | 0 | 0 | 0 | 0 | 6635702 | 0 | 0 | 3751161.5 | 6635702 |  |  | 3
SWWS00015A | SWFWMD | 2010 | H404-1 | Linked | H400 | Lower Hillsborough River Recovery Strategy Morris Bridge Sink | SWFWMD | 28.0768 | -82.3344 | Surface Water | No | This project will construct a pump station and pipeline components to divert surface water from the Morris Bridge Sinkhole to the upper pool of the Tampa Bypass Canal. A second pump station will be used to transfer water to the canal’s middle pool, where it can be conveyed through the reservoir to the LHR during low flow periods to help implement minimum flows. Includes required environmental monitoring. | Construct pump stations to divert surface water from the Morris Bridge Sink to the upper pool of the Tampa Bypass Canal and from the canal's middle pool to the Lower Hillsborough River during low flow periods to help meet minimum flows. Includes environmental monitoring. | Underway | 2024-10-01 | 2032-10-01 | Hillsborough River | SWF Tampa Bay | 2015 | Lower Hillsborough River |  | Lower Hillsborough River Recovery Strategy | 0 | 3.9 | 0 | 0 | 0 | 0 | FY2016-17 through FY2025-26 | 631241 | 20000 | 0 | 0 | 0 | 0 | 2.2.1.3 - Minimum Flows and Minimum Water Levels Recovery | WRD | 0 | FY2005-06 | FY2024-25 | 0 | 0 | 0 | 0 | 1349982 | 0 | 0 | 0 | 1349982 | Annual request. Project total does not include construction funds. |  | 4
SWWS00035K | SWFWMD | 2020 | H400-7 | Linked | H400 | Third Five-Year Assessment of the Lower Hillsbouirhg River Recovery Strategy | SWFWMD | 28.0175 | -82.3713 | Surface Water Storage | No | Third of three rule-required five-year assessments of the Lower Hillsborough River Recovery Strategy | Conduct the third and final five-year assessments of the Lower Hillsborough River Recovery Strategy. | Underway | 2023-08-01 | 2025-12-31 | Hillsborough River | SWF Tampa Bay | 2015 | Lower Hillsborough River |  | Lower Hillsborough River Recovery Strategy | 0 | 0 | 0 | 0 | 0 | 0 | FY2023-24 through FY2025-26 | 263943.88 |  | 0 | 0 | 0 | 0 | 2.2.1.3 - Minimum Flows and Minimum Water Levels Recovery | WRD | 0 | FY2019-20 | FY2019-20 | 0 | 0 | 0 | 0 | 263944 | 0 | 0 | 0 | 263944 |  |  | 5
| SWFWMD | 2025 | H400-13 | Linked | H400 | Lower Hillsborough River Biological Data Collection | SWFWMD | 28.0175 | -82.3713 | Other Project Type | No | This project includes hydrological, biological, chemical, bathymetric data collection and modeling in support of the Lower Hillsborough River Recovery Strategy (LHRRS). The LHRRS specifies that salinity, biological and water qualty information for the lower river will be evaluated as part of the recovery strategy. | Data collection in support of the Lower Hillsborough River Recovery Strategy (LHRRS) | Underway | 2019-10-01 | 2025-12-31 | Hillsborough River | SWF Tampa Bay | 2015 | Lower Hillsborough River |  | Lower Hillsborough River Recovery Strategy | 0 | 0 | 0 | 0 | 0 | 0 | FY24-25- FY2025-26 | 40000 | 50000 | 0 | 0 | 0 | 0 | 2.2.1.3 - Minimum Flows and Minimum Water Levels Recovery | WRD |  | FY2024-25 | FY2025-26 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 90000 |  |  | 6
| SWFWMD | 2010 | H529 |  |  | Mini-FARMS Program | Florida Department of Agriculture and Consumer Services | 27.3376 | -82.4352 | Agricultural Conservation | No | Mini-FARMS is a scaled down version of the District’s FARMS cost-share reimbursement program to implement agricultural BMPs on agricultural operations to conserve water and protect water quality within the District. Similar to the FARMS projects, the Mini-FARMS Program implements BMPs on agricultural operations to reduce Upper Floridan groundwater use and improve water quality conditions throughout the District. Under the Mini-FARMS Program guidelines, the District will reimburse growers 75 percent of their project costs up to $10,000 per project. | Implement the Mini-FARMS Program to implement BMPs on agricultural operations to reduce Upper Floridan groundwater use and improve water quality conditions throughout the District. | Design | 2024-10-01 | NA | SWUCA Water Bodies NTBWUCA Water Bodies DPCWUCA Water Bodies Shell Creek Prairie Creek Joshua Creek Horse Creek | SWF District-wide | 2015 | N/A |  | Southern WUCA | 0 | 2 | 0 | 0 | 0 | 0 | FY2018-19 through FY2025-26 | Annual Request | 500000 | 500000 | 500000 | 500000 | 500000 | 2.2.1.2 - Facilitating Agricultural Resource Management Systems | WRD | 0 | FY2007 | FY2024 | 0 | 0 | 0 | 0 | Annual Request | 0 | 0 | 0 | Annual Request |  |  | 7
| SWFWMD | 2023 | H807 | Linked | H017 | FARMS- Sizemore Group Automation | Sizemore Group Automation | 27.943 | -82.097 | Agricultural Conservation | No | Project components consist of five remotely operated irrigation pump stations, soil moisture sensors and a fertigation system.. | Water conservation through precision irrigation equipment to limit groundwater use. | Construction | 2022-08-23 | 2026-07-23 | DPCWUCA Water Bodies Howell Branch | SWF Tampa Bay |  | N/A |  | Tampa Bay WUCA | 0 | 0.0307 | 0 | 0 | 0 | 0 | FY2023-24 through FY2025-26 | 182857 | 0 | 0 | 0 | 0 | 0 | 2.2.1.2 - Facilitating Agricultural Resource Management Systems | WRD |  | FY23 | FY23 | 0 | 0 | 0 | 0 | 182857 | 0 | 60952 |  | 243809 |  |  | 8
| SWFWMD | 2025 | H817 | Linked | H017 | B 8 TURF CO., LLC | B 8 TURF CO., LLC | 27.404 | -82.092 | Agricultural Conservation | No | This ais an alternative water supply project using a five acre reservoir with one surface water pump station, weather station, filtration, automation of groundwater and surface water pumps, soil moisture probes, valves, fertigation systems, two center pivots, and the piping necessary to connect the surface water reservoir to the center pivot irrigation systems. | Groundwater conservation though the use of an alternative water supply and automation. | Construction | 2025-02-25 | 2026-02-25 | Upper Myakka River | SWF Southern |  | N/A |  | Southern WUCA | 0 | 0.13 | 0 | 0 | 0 | 0 | FY2025-26 | 751229 | 0 | 0 | 0 | 0 | 0 | 2.2.1.2 - Facilitating Agricultural Resource Management Systems | WRD |  | FY25 | FY25 | 0 | 0 | 0 | 0 | 751229 |  | 250410 |  | 1001639 |  |  | 9
| SWFWMD | 2025 | H821 | Linked | H017 | JAMES KEEN 62 | JAMES KEEN 62 | 27.605 | -82.829 | Agricultural Conservation | No | This is an alternative water supply project using a three acre reservoir with a linear overhead irrigation system with an automated surface water pump with a fertigation system, a weather station with soil moisture probes, and control structures. | Groundwater conservation though the use of an alternative water supply and automation. | Construction | 2024-09-24 | 2026-09-24 | Little Manatee River | SWF Southern |  | N/A |  | Southern WUCA | 0 | 0.082 | 0 | 0 | 0 | 0 | FY2025-26 | 380400 | 0 | 0 | 0 | 0 | 0 | 2.2.1.2 - Facilitating Agricultural Resource Management Systems | WRD |  | FY25 | FY25 | 0 | 0 | 0 | 0 | 380400 |  | 242300 |  | 662700 |  |  | 10
| SWFWMD | 2025 | H825 | Linked | H017 | BERRY RED FARMS, LLC | BERRY RED FARMS, LLC | 27.59 | -82.078 | Agricultural Conservation | No | This is an alternative water supply project using a three acre reservoir with one surface water pump station, filtration, a fertigation system, valves, mainline piping necessary to tie into the existing irrigation system, two weather stations with soil moisture probes, and automation of two groundwater wells. | Groundwater Conservation through the use of an alternative water supply and automation. | Construction | 2024-08-27 | 2026-08-27 | Manatee River (east Fork) | SWF Southern |  | N/A |  | Southern WUCA | 0 | 0.06 | 0 | 0 | 0 | 0 | FY2025-26 | 164640 | 0 | 0 | 0 | 0 | 0 | 2.2.1.2 - Facilitating Agricultural Resource Management Systems | WRD |  | FY25 | FY25 | 0 | 0 | 0 | 0 | 164640 |  | 54611 |  | 219251 |  |  | 11
| SWFWMD | 2025 | H826 | Linked | H017 | FD BERRIES USA LLC - Twitty Road South | FD BERRIES USA LLC - Twitty Road South | 27.401 | -81.385 | Agricultural Conservation | No | This is a precision irrigation project with automation of three irrigation pump stations, one weather station, six soil moisture sensors and a fertigation system. | Water conservation through precision irrigation equipment to limit groundwater use. | Construction | 2024-08-27 | 2026-05-27 | Kissimmee River | SWF Heartland |  | N/A |  | Southern WUCA | 0 | 0.025 | 0 | 0 | 0 | 0 | FY2025-26 | 119129 | 0 | 0 | 0 | 0 | 0 | 2.2.1.2 - Facilitating Agricultural Resource Management Systems | WRD |  | FY25 | FY25 | 0 | 0 | 0 | 0 | 119129 |  | 52000 |  | 171129 |  |  | 12
| SWFWMD | 2025 | H828 | Linked | H017 | G & G FARMS LLC - NORTH 40 | G & G FARMS LLC - NORTH 40 | 28.085 | -82.165 | Agricultural Conservation | No | This is an alternative water supply project using a 5 acre reservoir with two surface water pump stations, mainline piping and valves necessary to tie into the existing irrigation system, pump automation, fertigation, weather station, and two soil moisture probes. | Groundwater conservation through the use of an alternative water supply and automation. | Construction | 2024-08-27 | 2026-08-27 | Hillsborough River | SWF Tampa Bay |  | N/A |  | Dover/Plant City WUCA | 0 | 0.045 | 0 | 0 | 0 | 0 | FY2025-26 | 212246 | 0 | 0 | 0 | 0 | 0 | 2.2.1.2 - Facilitating Agricultural Resource Management Systems | WRD |  | FY25 | FY25 | 0 | 0 | 0 | 0 | 212246 |  | 70749 |  | 282995 |  |  | 13
| SWFWMD | 2025 | H830 | Linked | H017 | MCCLURE PROPERTIES, LTD - PHASE 2 | MCCLURE PROPERTIES, LTD - PHASE 2 | 27.584 | -82.112 | Agricultural Conservation | No | This is a precision automation project automation of one irrigation pump station, fertigation system, weather station, a soil moisture monitoring system, and the filters and piping necessary to convert from seepage to drip irrigation. | Water conservation through precision irrigation equipment to limit groundwater use. | Completed | 2024-11-19 | 2025-06-25 | Manatee River | SWF Southern |  | N/A |  | Southern WUCA | 0 | 0.045 | 0 | 0 | 0 | 0 | FY2025-26 | 195706 | 0 | 0 | 0 | 0 | 0 | 2.2.1.2 - Facilitating Agricultural Resource Management Systems | WRD |  | FY25 | FY25 | 0 | 0 | 0 | 0 | 195706 |  | 90299 |  | 286005 |  |  | 14
| SWFWMD | 2025 | H831 | Linked | H017 | GAPWAY MIXON CUPS, LLC | GAPWAY MIXON CUPS, LLC | 27.743 | 81.692 | Agricultural Conservation | No | This is a precision automation project automation of three irrigation pump stations, valve automation, fertigation system, weather station, and soil moisture monitoring system. | Water conservation through precision irrigation equipment to limit groundwater use. | Completed | 2025-02-24 | 2025-07-16 | Upper Peace River | SWF Southern |  | N/A |  | Southern WUCA | 0 | 0.02 | 0 | 0 | 0 | 0 | FY2025-26 | 64171 | 0 | 0 | 0 | 0 | 0 | 2.2.1.2 - Facilitating Agricultural Resource Management Systems | WRD |  | FY25 | FY25 | 0 | 0 | 0 | 0 | 64171 |  | 21391 |  | 85562 |  |  | 15
| SWFWMD | 2026 | H832 | Linked | H017 | T&T ENVIRONMENTAL, LLC - DESOTO GROVES | T&T ENVIRONMENTAL, LLC - DESOTO GROVES | 27.194 | -81.93 | Agricultural Conservation | No | This is an alternative water supply project using a 4.5 acre reservoir using two center pivots conected to an existing surface water pump system. The project also includes automated valves, fertigation system, water control structures, a weather station, soil moisture probes, and the mainline piping necessary to connect the surface water reservoir to two center pivot irrigation systems. | Groundwater conservation through the use of an alternative water supply and automation. | Construction | 2025-06-24 | 2026-06-24 | Peace River | SWF Southern |  | N/A |  | Southern WUCA | 0 | 0.13 | 0 | 0 | 0 | 0 | FY2025-26 | 652782 | 0 | 0 | 0 | 0 | 0 | 2.2.1.2 - Facilitating Agricultural Resource Management Systems | WRD |  | FY25 | FY25 | 0 | 0 | 0 | 0 | 652782 |  | 217595 |  | 870377 |  |  | 16
| SWFWMD | 2027 | H833 | Linked | H017 | MIDWAY FARMS, LLC - Raulerson Road | MIDWAY FARMS, LLC - Raulerson Road | 27.694 | -81.607 | Agricultural Conservation | No | This is a precision irrigation project automation of one irrigation pump station, valve automation, fertigation system, weather station, and soil moisture monitoring system. | Water conservation through precision irrigation equipment to limit groundwater use. | Construction | 2025-03-25 | 2026-03-25 | Kissimmee River Lake Istokpoga | SWF Heartland |  | N/A |  | Southern WUCA | 0 | 0.02 | 0 | 0 | 0 | 0 | FY2025-26 | 45468 | 0 | 0 | 0 | 0 | 0 | 2.2.1.2 - Facilitating Agricultural Resource Management Systems | WRD |  | FY25 | FY25 | 0 | 0 | 0 | 0 | 45468 |  | 15156 |  | 60624 |  |  | 17
| SWFWMD | 2028 | H834 | Linked | H017 | JIM RASH, INC - ZOFFAY ROAD | JIM RASH, INC - ZOFFAY ROAD | 27.768 | -81.553 | Agricultural Conservation | No | This is a precision irrigation project with a variable frequency drive for the irrigation pump and the automation of that pump station, valve automation, one weather station, two soil moisture sensors, and a fertigation system. | Water conservation through precision irrigation equipment to limit groundwater use. | Construction | 2025-06-24 | 2025-06-26 | KissimmeeRiver Lake Clinch Outfall | SWF Heartland |  | N/A |  | Southern WUCA | 0 | 0.018 | 0 | 0 | 0 | 0 | FY2025-26 | 64214 | 0 | 0 | 0 | 0 | 0 | 2.2.1.2 - Facilitating Agricultural Resource Management Systems | WRD |  | FY25 | FY25 | 0 | 0 | 0 | 0 | 64214 |  | 21405 |  | 85619 |  |  | 18
| SWFWMD | 2025 | H835 | Linked | H017 | Green Grass Farms of Hardee County | Green Grass Farms of Hardee County | 27.345 | 81.646 | Agricultural Conservation | No | This is an alternative water supply project using two 3- acre reservoirs with two linear overhead irrigation systems with automated surface water pumps and fertigation systems, a weather station with soil moisture probes and water control structures. | Groundwater conservation through the use of an alternative water supply and automation. | Construction | 2025-07-22 | 2026-07-22 | Peace River | SWF Heartland |  | N/A |  | Southern WUCA | 0 | 0.18 | 0 | 0 | 0 | 0 | FY2025-26 | 771933 | 0 | 0 | 0 | 0 | 0 | 2.2.1.2 - Facilitating Agricultural Resource Management Systems | WRD |  | FY25 | FY25 | 0 | 0 | 0 | 0 | 771933 |  | 401905 |  | 1173838 |  |  | 19
| SWFWMD | 2015 | N339 |  |  | Winter Haven #3 RW Interconnect, Storage/Pumping - Design & Construction | Winter Haven, City of | 27.9625 | -81.7091 | Reclaimed Water (for potable offset) | No | The project consists of design, permitting, and construction of 25,000 feet of 20-inch reclaimed water interconnect between the City's two reuse systems, a 5 mgd reclaimed water pump station, and a 5 million gallon storage tank. The project will transfer reclaimed water from the southern region to the northern service area. | Design, permitting, and construction of 25,000 feet of 20-inch reclaimed water interconnect between the City's two reuse systems, a 5 mgd reclaimed water pump station, and a 5 million gallon storage tank. | Construction Completed | 2013-10-25 | 2022-12-31 | SWUCA Water Bodies Peace Creek Drainage Canal | SWF CFWI-2 (including portion of Heartland) | 2015 | N/A |  | Southern WUCA | 0 | 0.3 | 0 | 0.3 | 5 | 5 | FY2011-12 through FY2025-26 | 2083025.44 | 0 | 0 | 0 | 0 | 0 | 2.2.2.3 - Reclaimed Water | WSD | 0 | FY2012 | FY2014 | 0 | 0 | 0 | 0 | 2750000 | 0 | 6716000 | 8429117.17 | 9466000 |  |  | 20
| SWFWMD | 2020 | N435 |  |  | Surface Water Aquifer Storage & Recovery | City of Bradenton | 27.4371 | -82.4915 | Groundwater Recharge | No | This project is for the design, third party review (TPR), permitting and construction of one ASR well (ASR-2) and associated facilities to help meet current and future potable water supply demands. The TPR and current project costs were approved by the Governing Board in FY2015. The benefit of this project is the storage of approximately 150 MG/yr of excess surface water flow during the wet season for potable use in the the Most Impacted Area (MIA) of the SWUCA during the dry season. This project will provide a cost effective storage alternative for available high surface water flows in the MIA of the SWUCA. | Design, permitting and construction of a 1.0 MGD ASR system. | Construction Completed | 2015-10-01 | 2023-12-01 | SWUCA Water Bodies | SWF Southern |  | N/A |  |  | 0 | 0 | 0 | 0 | 150 | 0 | FY2012-13 through FY2025-26 | 2251081 | 0 | 0 | 0 | 0 | 0 | 2.2.2.5 - Aquifer Recharge/Storage & Recovery Construction | WSD |  | FY2013 | FY2018 | 0 | 0 | 0 | 0 | 2350000 | 0 | 2350000 |  | 4700000 |  |  | 21
| SWFWMD | 2020 | N791 | Linked | N743 | Starkey Ranch Reclaimed Water Transmission Project, Phase C | Pasco County | 28.2032 | -82.6286 | Reclaimed Water (for potable offset) | No | This project is for the design and construction of reclaimed water transmission mains in the next phase of the Starkey Ranch development. The project will include approximately 5,700 feet of 12- to 16-inch transmission mains and other necessary appurtenances to provide up to 0.29 mgd of reclaimed water to mixed-use irrigation customers (residential, commercial, and institutional). | Designing, permitting and constructing of 5,700 feet of 12- to 16-inch reclaimed water transmission mains to provide up to 0.29 MGD of reclaimed water to the Starkey Ranch development in Pasco County. | Complete | 2017-12-31 | 2020-12-30 | NTBWUCA Water Bodies Magnolia-Aripeka Springs Direct Runoff to Gulf | SWF Tampa Bay | 2020 | N/A |  |  | 0.58 | 0.29 | 0.58 | 0.29 | 0 | 0 | FY2016-17 through FY2025-26 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2.2.3 - Reclaimed Water | WSD |  | FY2017 | FY2018 | 0 | 0 | 0 | 0 | 456800 | 0 | 456800 | 733280 | 913600 |  |  | 22
| SWFWMD | 2020 | N855 | N287 |  | South Hillsborough Aquifer Recharge Expansion (SHARP), Phase 2 | Hillsborough County | 27.7166 | -82.3353 | Groundwater Recharge | No | This project is for a third-party review of the County's 30 percent design, completion of design and permitting, and the initiation of construction for Phase 1 of the South Hillsborough Aquifer Recharge Expansion (SHARE) project. Pending third-party review and approval, project will construct 9,500 feet of transmission mains, two recharge wells (2 mgd each), eight monitoring wells, and associated appurtenances. The SHARE project expands upon the county's current recharge project (N287) and upon completion will consist of up to seven recharge wells with a total recharge flow of up to 14 mgd in Southern Hillsborough. | Complete a third-party review of Hillsborough County's 30 percent design, completion of design and permitting, and the initiation of construction for Phase 1 of the South Hillsborough Aquifer Recharge Expansion (SHARE) project. | Design | 2022-10-01 | 2023-09-01 | Upper Floridan Aquifer SWUCA Water Bodies Hillsborugh Bay Palm River McKay Bay | SWF Tampa Bay | 2020 | SWUCA SWIMAL |  | Northern Tampa Bay WUCA Recovery Strategy | 0 | 0 | 0 | 0 | 4 | 0 | FY2017-18 though FY2025-26 | 0 | $- | $- | $- | $- | $- | 2.2.1.1 - Aquifer Storage & Recovery Feasibility and Pilot Testing | WRD | NA | FY2018 | FY2020 | $- | $- | $- | $- | 4800000 | $- | 4900000 | 8245000 | 9700000 | No invoices received to date. Amendment 1 processing in Case to revise project schedule and Budget. Updated budget will be reduced to $8,217,640.00, due to the removal of 2 monitoring wells at RW-2 and RW-4 sites. |  | 23
| SWFWMD | 2020 | N868 |  |  | Polk County Utilities NERUSA Ernie Caldwell Blvd RW Transmission | Polk County Utilities | 28.2225 | -81.6242 | Reclaimed Water (for potable offset) | No | This project is for the design, permitting, and construction of approximately 10,300 feet of 16- to 24-inch reclaimed water transmission mains and necessary appurtenances to supply approximately 1,100 residential irrigation customers in the Ridgewood Lake DRI Property Areas of NERUSA. When connected, the project will supply approximately 0.414 mgd of reclaimed water to residential customers in the “Ridge Area” of the CFWI. | Designing, permitting and constructing 10,300 feet of 16- to 24-inch reclaimed water transmission mains to supply approximately 1,100 residential irrigation customers in the Ridgewood Lake in Polk County. | Complete | 2018-06-30 | 2020-06-30 | SWUCA Water Bodies Big Creek East Watershed | SWF CFWI-2 (including portion of Heartland) | 2020 | N/A |  | Southern WUCA | 0 | 0 | 0.41 | 0.41 | 0 | 0 | FY2017-18 though FY2025-26 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2.2.3 - Reclaimed Water | WSD | 0 | FY2018 | FY2019 | 0 | 0 | 0 | 0 | 1056500 | 0 | 1056500 | 1788980 | 2113000 |  |  | 24
| SWFWMD | 2020 | N973 |  |  | Winter Haven Consumption/Conservation Programs Data Management Software | Winter Haven, City of | 28.0164 | -81.7334 | PS and ICI Conservation | No | This project is the implementation of a software program that will promote and encourage water conservation by utility customers. The project will set up a software platform including a utility side dashboard and initially will be available for 19,000 customers. The program is expected to expand as advanced metering infrastructure is installed throughout the City over the next several years. The software will provide a customer portal log-in and graph customers water use over time, promote utility conservation incentives and rebates based on property appraiser data and water use data, compare water use to neighbors (social norming), detect customers side leaks and inform customers of the issue on a daily basis, and educate customers about watering restrictions based on actual daily water usage. | Implement a software program that will promote and encourage water conservation by utility customers in Winter Haven. | Underway | 2018-12-01 | 2024-09-01 | SWUCA Water Bodies | SWF CFWI-2 (including portion of Heartland) | 2020 | N/A |  | Southern WUCA | 0 | 0.016 | 0 | 0 | 0 | 0 | FY2018-19 through FY2025-26 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2.2.7 - Conservation Rebates and Retrofits | WSD | NA | FY2019 | FY2019 | 0 | 0 | 0 | 0 | 60000 | 0 | 60000 |  | 120000 |  |  | 25
| SWFWMD | 2015 | P189 | Linked | H089 | Aquifer Recharge Testing at Flatford Swamp | SWFWMD | 27.3929 | -82.1504 | Groundwater Recharge | No | This is a pilot project to test aquifer recharge at Flatford Swamp utilizing surface water. Aquifer recharge at the Flatford Swamp test well must meet primary drinking water standards and confirm arsenic mobilization is reduced. | Pilot Project to test aquifer recharge at Flatford Swamp. | Underway | 2017-10-01 | 2023-12-31 | SWUCA Water Bodies Upper Myakka River | SWF Southern | 2015 | SWUCA SWIMAL |  | Southern WUCA | 0 | 0 | 0 | 0 | 0 | 0 | FY2025-26 | 697973.1 | 451000 | 0 | 0 | 0 | 0 | 2.2.1.1 - Aquifer Storage & Recovery Feasibility and Pilot Testing | WRD | N/A | FY2023 | FY2026 | 0 | 0 | 0 | 0 | 1211000 | 0 | 0 | 0 | 1211000 |  |  | 26
| SWFWMD | 2020 | P925 | Linked | P280 | Optical Borehole Imaging Data Collection of LFA Wells | United States Geological Survey | 27.8196 | -81.6088 | Brackish Groundwater | No | This project collects optical borehole imaging data from LFA wells in Polk County. This data will aid in understanding the aquifer characteristics and groundwater quality in Polk County. The USGS will test and provide the processed data to the District. Nine LFA well sites have been identified for testing. | Conduct a study on a Lower Floridan aquifer optical borehole in Polk County. | Construction/Underway | 2017-10-01 | 2023-01-23 | SWUCA Water Bodies | SWF CFWI-2 (including portion of Heartland) | 2020 | N/A |  | Southern WUCA | 0 | 0 | 0 | 0 | 0 | 0 | FY2016-17 through FY2025-26 | 92400 | 0 | 0 | 0 | 0 | 0 | 2.2.1.1 - Aquifer Storage & Recovery Feasibility and Pilot Testing | WRD | 0 | FY2017 | FY2018 | 0 | 0 | 66800 | 66800 | 100200 | 0 | 0 | 0 | 167000 |  |  | 27
| SWFWMD | 2020 | P926 | Linked | P280 | Sources/Ages of Groundwater in the LFA in Polk County | United States Geological Survey | 27.8161 | -81.4413 | Brackish Groundwater | No | This project collects +A48:M48isotope data from LFA wells from various sites in Polk County. The groundwater analysis will determine the sources and ages of the water from productive zones within the LFA and lower portions of the Upper Floridan aquifer. This data will aid in understanding the LFA characteristics (including flow paths) and groundwater quality in Polk County. The USGS will test and provide the processed data to the District. Six LFA well sites have been identified for testing. | Collect isotope data from nine Lower Floridan Aquifer wells from various sites in Polk County to determine the sources and ages of the water from productive zones within the LFA and lower portions of the Upper Floridan aquifer. | Construction/Underway | 2017-10-01 | 2025-09-30 | SWUCA Water Bodies | SWF CFWI-2 (including portion of Heartland) | 2020 | N/A |  | Southern WUCA | 0 | 0 | 0 | 0 | 0 | 0 | FY2016-17 through FY2025-26 | 255475 | 0 | 0 | 0 | 0 | 0 | 2.2.1.1 - Aquifer Storage & Recovery Feasibility and Pilot Testing | WRD | 0 | FY2017 | FY2018 | 0 | 0 | 368300 | 368300 | 368300 | 0 | 0 | 0 | 736600 |  |  | 28
| SWFWMD | 2023 | P964 | Phased | NA | Water Use Evals for Non-Ag Users | TBD | 28.016 | -82.353 | PS and ICI Conservation | No | The Water Use Evaluations for Non-Agricultural Users will assist in meeting the District’s strategic goals associated with increased water use efficiency. This program will focus on promoting the implementation of water conservation projects by providing non-agricultural water users with water use evaluations to include a report with recommendations for improving water use efficiency. These evaluations and recommendations will steer quality projects toward the WISE program and will encourage participation of, but not be limited to, entities who historically have not participated in either the CFI or WISE programs. District staff will partner with utilities to select customers for evaluations, as well as evaluate individual water use permittees for participation. This funding request is to hire a third-party consultant to perform approximately 20 evaluations and develop the associated reports with water use efficiency recommendations. The third-party consultant shall also provide the District with a final report summarizing their key findings during the evaluations. Should actual costs be less than anticipated, the third-party consultant may perform more evaluations as the availability of funds allow. | Provide non-agricultural water users with water use evaluations to include a report with recommendations for improving water use efficiency. Funding is for a third-party consultant to perform the evaluations and develop the reports. | Design | TBD | TBD | Upper Floridan Aquifer, Hillsborough River, NTBWUCA Water Bodies, SWUCA Water Bodies | SWF District-wide |  | N/A |  |  | 0 | 0.011834 | 0 | 0 | 0 | 0 | FY2022-23 through FY2025-26 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2.2.7 - Conservation Rebates and Retrofits | WSD |  | FY2023 | FY2024 | 0 | 0 | 0 | 0 | 103400 | 0 | 0 | 0 | 103400 | This project is Districtwide, with 1 utility partner in each planning region. |  | 29
| SWFWMD | 2020 | Q050 |  |  | City of Venice Reclaimed Water Aquifer Storage Recovery | City of Venice | 27.134 | -82.403 | Aquifer Storage and Recovery | No | This project is for the design, permitting, construction, testing, and independent performance evaluation (IPE) of an Aquifer Storage and Recovery (ASR) system to store and recover at least 60 million gallons per year (mgy) of reclaimed water on-site at the City's Eastside Water Reclamation Facility, an advanced wastewater treatment plant. If constructed, ASR would let the City store excess reclaimed water in the wet season, to be used in the dry season when demand exceeds plant flow. Funding was previously approved for 30% design, third party review (TPR), final design, and construction permitting. The District required TPR because of project costs and complexity. The FY2022 funding request is for construction. Future funding will be for construction, testing, and operational permitting. | Complete design, permitting, construction, testing, and independent performance evaluation (IPE) of an ASR system at the City of Venice's Eastside Water Reclamation Facility to store excess reclaimed water in the wet season, to be used in the dry season. | Cancelled (Pending) | 2024-03-01 | 2026-03-16 | SWUCA Water Bodies Curry Creek Sarasota Bay | SWF Southern | 2020 | N/A |  | Southern WUCA Recovery Strategy | 0 | 0.17 | 0 | 0 | 15.3 | 0 | FY2019-20 through FY2025-26 | 42581 | 0 | 0 | 0 | 0 | 0 | 2.2.1.1 Alternative Water Supply Feasibility Research and Pilot Projects | WRD |  | FY2020 | FY2023 | 0 | 0 | 0 | 0 | 2744876 | 0 | 2744876 |  | 5489762 |  | City of Venice submitted a letter requesting to cancel the project, which is being processed currently though it is not finalized yet. | 30
| SWFWMD | 2020 | Q064 |  |  | Northwest Hillsborough Aquifer Recharge Program Phase 2 (Direct Aquifer Recharge) | Hillsborough County | 28.052 | -82.5854 | Groundwater Recharge | No | This project includes completion of a direct aquifer recharge feasibility study, which includes the construction and testing of three exploratory wells necessary to evaluate recharge locations for the North Hillsborough Aquifer Recharge Program (NHARP). If approved, the study will aid in the determination of the hydrogeological characteristics and water quality of the targeted Avon Park Formation of the Upper Floridan aquifer and the approximate depth of the base of the underground source of drinking water (USDW) in the general vicinity of NHARP. Information from this study will support selection of the recharge zone and aid in pursuing permits for future recharge wells not included in this funding request. The benefit of this project is completion of a feasibility study to determine the viability of expanding the use of reclaimed water for aquifer recharge to manage the rate of saltwater intrusion and aid in recovery of aquifer water levels in the Northern Tampa Bay Water Use Caution Area (NTBWUCA). | Complete a direct aquifer recharge feasibility study to evaluate recharge locations for the North Hillsborough Aquifer Recharge Program to determine the viability of expanding the use of reclaimed water for aquifer recharge. | underway | 2019-12-01 | 2025-03-31 | Upper Floridan Aquifer NTBWUCA Water Bodies Old Tampa Bay | SWF Tampa Bay | 2020 | NTB SWIMAL |  | Northern Tampa Bay WUCA Recovery Strategy | 0 | 0 | 0 | 0 | 0 | 0 | FY2019-20 through FY2025-26 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2.1.1 Alternative Water Supply Feasibility Research and Pilot Projects | WRD | NA | FY2020 | FY2020 | 0 | 0 | 0 | 0 | 750000 | 0 | 750000 |  | 1500000 | No invoices received to date. Amendment #3 routing in Case. This Amendment revises the SOW from three to two exploratory wells, reduces the District funding share from $750,000 to $500,000, and extends the CFA contract expiration date. |  | 31
| SWFWMD | 2020 | Q066 |  |  | Polk County NERUSA Lake Wilson Road Reuse Project | Polk County | 28.254 | -81.59 | Reclaimed Water (for potable offset) | No | This project is for the design, permitting, and construction of approximately 5,000 feet of reclaimed water transmission mains and other necessary appurtenances to supply approximately 1,025 multi-family homes and approximately 1 acre of common areas in the Victoria Park, Echelon-Ovation, Lake Bluff and Crystal Ridge subdivisions in the North East utility Service Area. This project will supply reclaimed water for residential irrigation use in the Central Florida Water Initiative area (CFWI). The benefit is the supply of 0.18 mgd of reclaimed water to residential irrigation customers for an anticipated 0.17 mgd of water savings within the CFWI. | Expanding reclaimed water use in Polk County to provide reuse to offset current and future residential and recreational water use. | Completed | 2019-12-01 | 2024-12-31 | SWUCA Water Bodies Big Creek East Watershed | SWF CFWI-2 (including portion of Heartland) | 2020 | N/A |  | Southern WUCA Recovery Strategy | 0 | 0 | 0 | 0.18 | 0 | 0 | FY2019-20 through FY2025-26 | 0 |  | 0 | 0 | 0 | 0 | 2.2.2.3 - Reclaimed Water | WSD |  | FY2020 | FY2020 | 0 | 0 | 0 | 0 | 262750 | 0 | 262750 | 0 | 525500 |  |  | 32
| SWFWMD | 2020 | Q067 |  |  | Polk County NERUSA Southeast Reuse Loop Project | Polk County | 28.208 | -81.593 | Reclaimed Water (for potable offset) | No | This project is for the design, permitting and construction of approximately 24,800 feet of reclaimed water transmission mains and other necessary appurtenances to construct a loop to supply approximately 1,365 homes in the Southeast reuse portion of the North East Utility Service Area and to enable supply to future planned subdivisions. The benefit of this project is the supply of 0.522 mgd of reclaimed water to residential irrigation customers for an anticipated 0.522 mgd of water savings within the CFWI. Goal to improve Winter Haven Chain of Lakes and Ridge Lakes. | Expanding reclaimed water use in Polk County to provide reuse to offset current and future residential and recreational water use. | Completed | 2019-12-01 | 2022-06-01 | SWUCA Water Bodies Big Creek East Watershed | SWF CFWI-2 (including portion of Heartland) | 2020 | N/A |  | Southern WUCA Recovery Strategy | 0 | 0 | 0 | 0.522 | 0 | 0 | FY2019-20 through FY2025-26 | 0 |  | 0 | 0 | 0 | 0 | 2.2.2.3 - Reclaimed Water | WSD |  | FY2020 | FY2021 | 0 | 0 | 0 | 0 | 2186750 | 0 | 2186750 |  | 4373500 |  |  | 33
| SWFWMD | 2020 | Q105 |  |  | Citrus County Sugarmill Woods Golf Course Reuse Project | Citrus County | 28.718 | -82.512 | Reclaimed Water (for potable offset) | No | This project includes the design, permitting, and construction of approximately 22,000 feet of transmission mains, a 1.0 million gallon storage tank, a 1.0 mgd pump station, a 0.5 mgd booster station and other necessary appurtenances to supply 0.50 mgd of reclaimed water to replace 0.375 mgd of groundwater used for irrigation at the Sugarmill Woods gold courses (one 18 hole and one 9 hole) within the Chassahowitzka Springs Springshed. This will supply and utilize 0.50 mgd of reclaimed water for golf course irrigation use in the Chassahowitzka Springs Springshed. Improves northern coastal spring system. | Constructing a reclaimed water expansion in Citrus County. | Underway | 2019-10-01 | 2024-06-30 | Chassahowitzka River Baird Creek | SWF Northern (excluding CFWI) | 2020 | N/A |  |  | 0 | 0 | 0 | 0.5 | 0 | 0 | FY2019-20 through FY2025-26 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2.2.3 - Reclaimed Water | WSD | NA | FY2020 | FY2021 | 250000 | 0 | 0 | 250000 | 1834000 | 0 | 1834000 |  | 3918000 |  |  | 34
| SWFWMD | 2020 | Q113 |  |  | Plant City McIntosh Park Indirect Potable Reuse Feasibility Study | Plant City | 28.0747 | -82.1333 | Reclaimed Water (for potable offset) | No | This project is for a feasibility study by Plant City to develop an indirect potable reuse project concept to utilize up to 1.5 mgd of reclaimed water for aquifer recharge to develop up to 0.75 mgd of new potable water supply. This project will verify treatment of source water including pilot testing to simulate full-scale treatment, UIC permitting for exploratory well, groundwater modeling and water quality sampling. An initial evaluation for the project was fully funded by the City to assess the level of treatment expected from the City's proposed reclaimed stormwater wetland treatment system and any additional treatment requirements for indirect potable reuse. The project will include a feasibility study by Plant City to develop an indirect potable reuse project to utilize up to 1.5 mgd of reclaimed water for aquifer recharge to develop approximately 0.75 mgd of new potable water supplies. | Study looking into the feasibility of using excess reclaimed water for potable use. | Complete | 2020-05-01 | 2022-06-30 | NTBWUCA Water Bodies Mill Creek East Canal Itchepackasassa Creek Blackwater Creek Hillsborough River | SWF Tampa Bay | 2020 | N/A |  | Dover Plant City WUCA | 0 | 0 | 0 | 0.75 | 0 | 0 | FY2019-20 through FY2025-26 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2.2.3 - Reclaimed Water | WSD | 0 | FY2020 | FY2020 | 0 | 0 | 0 | 0 | 300000 | 0 | 300000 | 0 | 600000 | Project completed, still waiting on invoices for final disbursement. |  | 35
| SWFWMD |  | Q139 |  |  | North Port Direct Potable Reuse Feasibility | City of North Port | 27.051 | -82.2447 | Reclaimed Water (for potable offset) | No | A direct potable reuse (DPR) feasibility study to provide information on the potential future development of a DPR project for new potable water supply. The project wil incldue data collection and laboratory services necessary to determine the quantity and quality of water sources. Source water characterization will include regulated, unregulated, and emerging constituents. The study will also include a desktop evaluation and costing of available advanced treatment technologies for reclaimed water. | Direct potable reuse (DPR) feasibility study on the potential future development of a DPR project for new potable water supply. | Complete | 2020-10-01 | NA | SWUCA Water Bodies | Southern |  | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | FY2020-21 through FY2025-26 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2.2.3 - Reclaimed Water | WSD |  | FY2021 | FY2021 | 0 | 0 | 0 | 0 | 125000 | 0 | 125000 |  | 250000 |  |  | 36
| SWFWMD |  | Q142 |  |  | Chesnut Park Aquifer Storage Recovery and Recharge | Pinellas County | 28.082 | -82.7031 | Groundwater Recharge | No | This project is 30% design, third-party review (TPR) and additional FY21 design and construction for this aquifer storage and recovery (ASR) and aquifer recharge (AR) project to divert excess surface water from Lake Tarpon to an existing ASR well and proposed AR facility to supplement the reclaimed water supply during dry periods, restore water level elevations in the NTBWUCA, and facilitate freshening of the aquifer. If constructed, this project would include design, permitting, construction, testing, and independent performance evaluation (IPE) of one recharge well, two monitoring wells, and surface facilities. District funding is for eligible FY21 design, including 30% design and TPR. The County will apply for future funding to complete design, permitting, construction, start-up, testing, and IPE. | Completion of 30% design, TPR and additional FY21 design and construction for ASR and AR project to divert excess surface water from Lake Tarpon to supplement reclaimed water during dry periods and restore NTBWUCA water levels. | Design | 2024-03-01 | 2025-02-28 | Upper Floridan Aquifer NTBWUCA Water Bodies Lake Tarpon Canal Safety Harbor Old Tampa Bay | SWF Tampa Bay |  | NTB SWIMALs |  |  | 0 | 0 | 0 | 0 | 0 | 0 | FY2020-21 through FY2025-26 | 93754.26 | 0 | 2779875 | 926625 | 0 | 0 | 2.2.2.5 - Aquifer Recharge/Storage & Recovery Construction | WSD |  | FY2021 | FY2021 | 0 | 0 | 0 | 0 | 4600000 | 0 | 4600000 |  | 9200000 |  |  | 37
| SWFWMD |  | Q145 |  |  | Advanced Irrigation System | Longboat Key Club | 27.3749 | -82.6226 | PS and ICI Conservation | No | Installation of advanced irrigation system including high efficiency spray heads and remote communication for the Resort at Longboat Key Club's Harbourside golf course, a private course. This higher level of precision irrigation will result in a reduction of irrigated acreage and better distribution uniformity of irrigation events. This project also includes the replacement of turf with native landscaping to further reduce irrigable acreage. | Installation of advanced irrigation system including high efficiency spray heads and remote communication. | Construction Completed | 2021-10-01 | 2022-04-01 | SWUCA Water Bodies | SWF Southern |  | N/A |  |  | 0 | 0.0946 | 0 | 0 | 0 | 0 | FY2020-21 through FY2025-26 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2.2.7 Conservation | WSD |  | FY2021 | FY2021 | 0 | 0 | 0 | 0 | 508516 | 0 | 606484 |  | 1115000 |  |  | 38
| SWFWMD |  | Q159 |  |  | Sarasota County - Bee Ridge Water Reclamation Facility Aquifer Recharge (Q159) | Sarasota County | 27.3 | -82.395 | Groundwater Recharge | No | This project is for recharge of reclaimed water meeting high-level disinfection standards into the Upper Floridan aquifer for SWUCA/MIA recovery. The project components include two recharge wells, three monitoring wells, a pump station, interconnecting piping, appurtenances necessary for recharge, monitoring and testing. The County will fund all permitting, design, bidding and construction of one recharge well, one monitoring well, the pump station, interconnecting piping, appurtenances necessary for recharge, monitoring and testing. District funding is FY21 for construction of one recharge well, two monitoring wells, and testing. | Construction of two recharge and three monitor wells, pump station, interconnecting piping, and appurtenances for the recharge of reclaimed water meeting high-level disinfection standards into the Upper Floridan aquifer for SWUCA/MIA recovery. | Underway | 2020-10-01 | 2023-12-31 | Upper Floridan Aquifer SWUCA Water Bodies | SWF Southern |  | SWUCA SWIMALs |  | Southern WUCA Recovery Strategy | 0 | 5 | 0 | 0 | 0 | 0 | FY2020-21 through FY2025-26 | 744163.59 | 0 | 0 | 0 | 0 | 0 | 2.2.1.1 Alternative Water Supply Feasibility Research and Pilot Projects | WRD | 0 | FY2021 | FY2021 | 0 | 0 | 0 | 0 | 915511 | 0 | 915511 |  | 1831022 |  |  | 39
| SWFWMD |  | Q160 |  |  | Sarasota County Honore Avenue Reclaimed Water Transmission | Sarasota County | 27.174 | -82.445 | Reclaimed Water (for potable offset) | No | This project is for the design, permitting and construction of approximately 17,500 feet of reclaimed water transmission mains and other necessary appurtenances to supply approximately 1,066 homes within the Palmer Ranch portion of the Sarasota County reclaimed water service area and to enable supply to future planned subdivisions. | Design, permitting and construction of 17,500 feet of reclaimed water transmission mains and other appurtenances to supply 1,066 homes in the Palmer Ranch portion of the Sarasota County service area and enable future expansion. | Underway | 2020-10-01 | 2026-04-07 | SWUCA Water Bodies | SWF Southern |  | N/A |  | Southern WUCA Recovery Strategy | 0 | 0.53 | 0 | 0 | 0 | 0 | FY2020-21 through FY2025-26 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2.2.3 - Reclaimed Water | WSD |  | FY2021 | FY2023 | 0 | 0 | 0 | 0 | 1500000 | 0 | 1500000 |  | 3000000 |  |  | 40
| SWFWMD |  | Q184 | Linked | N905, Q216 | Southeast Wellfield Implementation | Polk Regional Water Cooperative | 27.8926 | -81.4482 | Brackish Groundwater | No | The final design, permitting, and construction of the Southeast Wellfield Water Treatment Facility. Project components include a reverse osmosis facility and brackish water wellfield located east of Lake Wales. The project will provide alternative water supply for participating members of the Polk Regional Water Cooperative, which will be delivered by a regional transmission system developed as a companion project (Q216), and builds upon the conceptual and preliminary design funded under project N905. | The final design, permitting, and construction of the Southeast Wellfield Water Treatment Facility | Construction | 2024-10-01 | 2028-11-30 | Upper Floridan Aquifer SWUCA Water Bodies | SWF CFWI-2 (including portion of Heartland) |  | N/A |  |  | 0 | 12.5 | 0 | 0 | 0 | 0 | FY2020-21 through FY2025-26 | 11625000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 2.2.2.4 Brackish Groundwater Development | WSD |  | FY2020 | FY2026 | 0 | 0 | 6750000 | 9109987 | 110940000 | 0 | 127480013 | 232755000 | 247530000 |  |  | 41
| SWFWMD |  | Q209 |  |  | Polk County Direct Potable Reuse Feasibility and Pilot Demo | Polk County | 27.174 | -82.445 | Reclaimed Water (for potable offset) | No | Project is a direct potable reuse (DPR) feasibility study and 14,400 gpd educational/testing pilot project by Polk County to test the development of a future DPR project for new potable water supply. The project includes data collection, laboratory services, design, permitting, construction and demonstration testing involving a field scale investigation of the advanced treatment of reclaimed water and at least one year of education and testing. | Direct potable reuse (DPR) feasibility study and 14,400 gpd educational/testing pilot project by Polk County to test the development of a future DPR project for new potable water supply. | Complete | 2020-10-01 | 2022-12-30 | SWUCA Water Bodies | SWF CFWI-2 (including portion of Heartland) |  | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | FY2020-21 through FY2025-26 | 412196 | 0 | 0 | 0 | 0 | 0 | 2.2.2.3 - Reclaimed Water | WSD |  | FY2021 | FY2021 | 0 | 0 | 0 | 0 | 795000 | 0 | 1796582 |  | 2591582 |  |  | 42
| SWFWMD |  | Q241 |  |  | TBW Southern Hillsborough County Transmission Expansion | Tampa Bay Water | 27.865 | -82.205 | Distribution/Transmission Capacity | No | The Project consists of the Third-Party Review (TPR), design, permitting and construction of a potable water transmission interconnection to supply additional alternative water from the Tampa Bay Water’s High Service Pump Station to Hillsborough County. The transmission interconnection will be approximately 26 miles long and is expected to have a max daily capacity of 65 million gallons per day (MGD). The pipeline will deliver only alternative water supplied under normal operating conditions. | Design, permitting and construction of approximately 26-mile potable water pipeline to supply alternative water from TBW’s High Surface Pump Station to South Hillsborough County. It is expected to deliver 65 MGD maximum day capacity. | Design | 2025-12-01 | 2029-01-22 | SWUCA Water Bodies | SWF Southern |  | N/A |  | Southern SWUCA | 0 | 0 | 0 | 0 | 0 | 65 | FY2022-23 through FY2025-26 | 3536729.76 | 17500000 | 37231598 | 37231598 | 37231597 | 0 | 2.2.2.2 Regional Potabe Water Interconnects | WSD |  | FY2022 | FY2026 | 0 | 0 | 2900000 | 2900000 | 145054000 | 0 | 290755630 | 386804100.49 | 438709630 |  |  | 43
| SWFWMD |  | Q215 |  |  | Demand Mgmnt Program Phase 2 | Tampa Bay Water | 28.052 | -82.5612 | PS and ICI Conservation | No | Financial incentives and services to customers for up to ten conservation activities, including: single family high-efficiency toilets; multi-family high-efficiency toilets; commercial industrial institutional (CII) high-efficiency valve type toilets; CII tank type toilets; 0.5 gallon per flush urinals; pre-rinse spray valves; commercial conveyor type energy star dishwashers; cooling tower optimization equipment; soil moisture sensor and evapotranspiration (ET) irrigation controllers; and landscape efficiency incentives. Also included is program promotion and administrative costs. | Financial incentives and services to customers for up to ten conservation activities. Also included is program promotion and administrative costs to ensure the success of the program. | Underway | 2020-10-01 | 2025-12-30 | NTBWUCA Water Bodies |  | SWF Tampa Bay | N/A |  |  | 0 | 0.93 | 0 | 0 | 0 | 0 | FY2020-21 through FY2025-26 | 755274 | 0 | 0 | 0 | 0 | 0 | 2.2.2.7 Conservation | WSD |  | FY2021 | FY2021 | 0 | 0 | 0 | 0 | 1432238 | 0 | 1432238 |  | 2684476 |  |  | 44
| SWFWMD |  | Q216 | Linked | N905, Q184 | Regional Transmission Southeast | Polk Regional Water Cooperative | 27.8926 | -81.4482 | Distribution/Transmission Capacity | No | This project is for the final design, permitting, and construction of the Southeast Wellfield Regional Transmission System. Project components include approximately 43 miles of pipeline extending from the Southeast Wellfield Water Treatment Facility located east of Lake Wales to multiple municipalities along the US-27 and Hwy-60 corridors. This project will deliver alternative water supply to members of the Polk Regional Water Cooperative. | The final design, permitting, and construction of the Southeast Wellfield's Regional Transmission System | Construction | 2024-08-01 | 2028-11-30 | Upper Floridan Aquifer SWUCA Water Bodies | SWF CFWI-2 (including portion of Heartland) |  | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 12.5 | FY2020-21 through FY2025-26 | 14572000 | 26083215 | 14447326 | 0 | 0 | 0 | 2.2.2.2 Regional Interconnect | WSD |  | FY2020 | FY2026 | 0 | 0 | 8388487 | 8388487 | 76013000 |  | 89699113 | 156976000 | 174100600 |  |  | 45
| SWFWMD |  | Q245 |  |  | Conservation - Pinellas County AMI Metering Analytics Project | Pinellas County | 27.9649 | -82.8008 | PS and ICI Conservation | No | Implementation of a software program that will promote and encourage water conservation by utility customers. This project will allow software platform setup, including a utility side dashboard, and associated training and will be available for 112,900 retail potable water customers. The software will: notify customers of suspected leaks as they occur; regularly analyze actual daily or hourly water use and notify customers of potential violations of watering restrictions; alert customers to a pre-set threshold usage amount; alert customers about faulty rain or soil moisture sensor based on weather data and daily water use; compare individual customer water use to that of similar households (social norming); and provide a customer portal log-in and graph customers water use over time. | Implementing a software program that will promote and encourage water conservation by utility customers in the NTBWUCA for the purpose of conserving an estimated 111,100 gpd. | Underway | 2021-10-01 | 2025-10-01 | NTB WUCA Water Bodies | [5 empty] | 0 | 0.1111 | 0 | 0 | 0 | 0 | FY2021-22 through FY2025-26 | 47662.31 | 0 | 0 | 0 | 0 | 0 | 2.2.2.7 Conservation Rebates and Retrofits | WSD |  | FY2022 | FY2022 | 0 | 0 | 0 | 0 | 139414 | 0 | 139414 | 0 | 278828 |  |  | 46
| SWFWMD |  | Q256 |  | Q387 | Conservation - St. Petersburg Sensible Sprinkling Program - Phase 10 | St. Petersburg, City of | 27.786 | -82.695 | PS and ICI Conservation | No | Make available approximately 300 irrigation evaluations to single family, multi-family and commercial customers. This will include program administration and evaluations with recommendations for optimizing the use of water outdoors through Florida-friendly Landscaping TM practices and other efficient irrigation best management practices. Approximately 300 rain sensor devices will be provided and installed for project participants who do not have a functioning device. Also included are educational materials, program promotion, follow-up evaluations and surveys. | Financial incentives and services to customers for residential irrigation system | Construction/Underway | 2021-10-01 | 2022-10-01 | NTB WUCA Water Bodies |  | 2020 |  | NA |  | 0 | 0.0549 | 0 | 0 | 0 | 0 | FY2021-22 through FY2025-26 | 45706.1 | 0 | 0 | 0 | 0 | 0 | 2.2.2.7 Conservation Rebates and Retrofits | WSD |  | FY2022 | FY2022 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000 | 0 | 100000 |  |  | 47
| SWFWMD |  | Q265 |  |  | Conservation - North Port Water Distribution Ridgewood/Lamplighter Area Looping | North Port, City of | 27.05 | -82.05 | PS and ICI Conservation | No | Construction of approximately 4,900 feet of new potable water lines and associated components necessary to eliminate system dead ends. This is considered a utility-based supply side conservation project and will reduce routine flushing in two areas by allowing potable water circulation in the central area of the City. | construction of appox. 4,900 feet of new potable water lines and associated components necessary to eliminate system dead ends. utility-based supply side conservation project and will reduce routine flushing in two areas. | Underway | 2022-01-01 | 2025-04-15 | SWUCA Water Bodies | SWF Southern |  | N/A |  | Southern SWUCA | 0 | 0.0145 | 0 | 0 | 0 | 0 | FY2021-22 through FY2025-26 | 156555 | 0 | 0 | 0 | 0 | 0 | 2.2.2.7 Conservation Rebates and Retrofits | WSD |  | FY2022 | FY2022 | 0 | 0 | 0 | 0 | 173950 | 0 | 173950 | 339900 | 347900 |  |  | 48
| SWFWMD |  | Q266 |  |  | Conservation - Polk County Florida Water Star Builder Reimbursement Program | Polk County | 27.8985 | -81.8457 | PS and ICI Conservation | No | Make available financial incentives to home builders for building homes to Florida Water Star (FWS) standards and submitting proof of FWS certification for these homes. FWS homes meet specific water-efficiency criteria inside the homes in appliances and fixtures and outside the homes in landscape and irrigation design and installation. This project will provide a $1,000 rebate per home for home builders to assist with the additional costs associated with building and certifying approximately 40 FWS-certified homes. | Financial incentives to home builders for building homes to Florida Water Star (FWS) standards and submitting FWS certification.The Project will provide a $1,000 rebate per home to assist with costs associated with building 40 FWS-certified homes. | Complete | 2022-01-01 | 2023-12-31 | SWUCA Water Bodies | SWF Southern |  | N/A |  | Southern SWUCA | 0 | 0.00526 | 0 | 0 | 0 | 0 | FY2021-22 through FY2025-26 | 18000 | 0 | 0 | 0 | 0 | 0 | 2.2.2.7 Conservation Rebates and Retrofits | WSD |  | FY2022 | FY2022 | 0 | 0 | 0 | 0 | 20000 | 0 | 20000 | 0 | 40000 |  |  | 49
| SWFWMD |  | Q267 |  |  | Conservation - PRWC Demand Management Implementation | Polk Regional Water Cooperative | 27.8985 | -81.8457 | PS and ICI Conservation | No | Make available financial incentives and services to residential and commercial customers for up to nine conservation activities, including: high-efficiency toilet rebates; 0.5 gallon per flush urinals; enhanced conservation kits, standard conservation kits, vouchers for toilet and installation, soil moisture sensors, evapotranspiration (ET) irrigation controllers, landscape irrigation audits, and rain sensors. Also included is program promotion and administrative costs.. | Water conservation program for up to nine conservation activities, including: HE toilet rebates; 0.5 gpf urinals; conservation kits, vouchers for toilet and installation, SMS, (ET) irrigation controllers, irrigation audits, and rain sensors. | Construction/Underway | 2021-10-01 | 2025-04-01 | SWUCA Water Bodies | SWF Heartland, CFWI |  | N/A |  | Southern SWUCA | 0 | 0.012519 | 0 | 0 | 0 | 0 | FY2021-22 through FY2025-26 | 92126 | 0 | 0 | 0 | 0 | 0 | 2.2.2.7 Conservation Rebates and Retrofits | WSD |  | FY2022 | FY2022 | 0 | 0 | 0 | 0 | 102679 | 0 | 102679 | 0 | 205358 |  |  | 50
| SWFWMD |  | Q268 |  |  | Reclaimed - BRU Taylor Road Area Transmission | Braden River Utilities | 27.448 | -82.345 | Reclaimed Water (for potable offset) | No | This project is for the third-party review (TPR) and construction of approximately 16,000 feet of reclaimed water mains, a SCADA system, a pump station and other necessary appurtenances to supply approximately 2,400 residential homes, common areas and a 27-hole golf course within the Taylor Road development of Lakewood Ranch in Manatee and Sarasota counties. The FY2022 funding request is for completion of third-party review and initiating construction. | This project is for the third-party review (TPR) and construction of approximately 16,000 feet of reclaimed water mains, a SCADA system, a pump station and other necessary appurtenances to supply approximately 2,400 residential homes, common areas and a 27-hole golf course within the Taylor Road development of Lakewood Ranch in Manatee and Sarasota counties. | Underway | 2023-09-25 | 2024-12-31 | SWUCA Water Bodies | SWF Southern |  | N/A |  | Southern SWUCA | 0 | 0 | 0 | 1.57 | 0 | 0 | FY2021-22 through FY2025-26 | 0 | 0 |  | 0 | 0 | 0 | 2.2.2.3 - Reclaimed Water | WSD |  | FY2022 | FY2022 | 0 | 0 | 0 | 0 | 3550000 | 0 | 3550000 | 6925000 | 7100000 |  |  | 51
| SWFWMD |  | Q272 | Linked | Q212 | PRMRWSA Reservoir No. 3 Project | Peace River Manasota Regional Water Supply Authority | 27.079 | -82.037 | Surface Water Storage | No | The preliminary design, third party review, final design, permitting, and construction of the Peace River Reservoir No. 3 Project. Project components include a 9 BG raw water storage reservoir, new river intake pump station, a reservoir pump station, and conveyance pipelines to transport water from the new pumping station to the reservoir and treatment facility. The project will provide a third off-stream raw water reservoir at the Peace River Water Treatment Facility in DeSoto County, which will couple with a future treatment facility expansion to meet regional demands with alternative water sources in the SWUCA. | Preliminary design, third party review, final design, permitting, and construction of the 9 bg Peace River Reservoir No. 3 and raw water intake structure for the Peace River Water Treatment Facility in southern DeSoto County. | Construction | 2025-07-01 | 2028-12-31 | SWUCA Water Bodies | SWF Southern |  | N/A |  | Southern SWUCA | 0 | 0 | 0 | 0 | 9300 | 0 | FY2021-22 through FY2025-26 | 642446 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 2.2.2.1 Surface Water | WSD |  | FY2022 | FY2026 | 0 | 0 | 24800000 | 24800000 | 115700000 | 0 | 224577000 | 335067796 | 375077000 |  |  | 52
| SWFWMD |  | Q274 |  |  | Reclaimed - Zephyrhills to Pasco County Reclaimed Water Interconnect | Zephyrhills, City of | 28.252 | -82.195 | Reclaimed Water (for potable offset) | No | :Design, permitting and construction of approximately 10,000 feet of reclaimed water transmission, a 1 mgd booster pump station and other necessary appurtenances to interconnect the City’s reclaimed water system to Pasco County’s reclaimed water system to meet diurnal and seasonal County reclaimed water demands. The project will enable the supply of reclaimed water to future customers in the Northern Tampa Bay Water Use Caution Area (NTBWUCA). | Design, permitting and construction of approximately 10,000 feet of reclaimed water transmission, | Underway | 2022-12-01 | 2024-12-01 | NTB WUCA Water Bodies | SWF Tampa Bay |  | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | FY2021-22 through FY2025-26 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2.2.3 - Reclaimed Water | WSD |  | FY2022 | FY2022 | 0 |  |  | 0 | 880000 | 0 | 880000 |  | 1760000 |  |  | 53
| SWFWMD |  | Q304 | Linked | Q179 | City of Venice Toilet Rebate and Retrofit, Phase 9 | Venice, City of | 27.133 | -82.394 | PS and ICI Conservation | No | : Make available financial incentives to residential and commercial customers for the replacement of conventional toilets with high-efficiency toilets which use 1.28 gallons per flush or less and for the replacement of conventional urinals with high-efficiency urinals which use 0.5 gallons per flush or less. This project will include rebates for the replacement of approximately 175 high flow toilets and/or urinals. In addition, approximately 400 do-it-yourself conservation kits will be distributed. These include educational materials, low-flow showerheads, and leak detection dye tablets. Also included are educational materials, program promotion, and surveys necessary to ensure the success of the program. Should actual costs be less than anticipated, the Cooperator may perform more installations/rebates as the availability of funds allow. | Make available financial incentives to residential and commercial customers for the replacement of 175 conventional toilets with high-efficiency toilets. This project will include rebates, program administration and 400 conservation kits. | Construction/ Underway | 2024-04-15 | 2024-12-31 | SWUCA Water Bodies | SWF Southern |  | N/A |  |  | 0 | 0.005 | 0 | 0 | 0 | 0 | FY2022-23 through FY2025-26 | 10700.46 | 0 | 0 | 0 | 0 | 0 | 2.2.2.7 Conservation Rebates and Retrofits | WSD |  | FY23 | FY23 | 0 | 0 | 0 | 0 | 16500 | 0 | 16500 |  | 33000 |  |  | 54
| SWFWMD |  | Q306 | Linked | Q138 | WRWSA Irrigation Eval Program, phase 7 | Withlacoochee Regional Water Supply Authority | 28.822 | -82.493 | PS and ICI Conservation | No | Make available financial incentives to customers for approximately 192 irrigation system evaluations within Marion, Citrus and Hernando counties and The Villages Development Districts. Participating utilities will assist in providing customers with recommendations for optimizing the use of water outdoors through Florida-Friendly Landscaping TM practices and recommending other efficient irrigation best management practices. For select customers, the project could also include performing irrigation system modifications and rain sensor installs for project participants who do not have a functioning device. Also included is program administration, educational materials, program promotion, follow-up evaluations and surveys necessary to ensure the success of the program. Should actual costs be less than anticipated, the Cooperator may perform more installations/rebates as the availability of funds allow. | Provide 192 irrigation system evaluations for customers within WRWSA member utilities. Provides for optimizing of outdoor water use through Florida-Friendly Landscaping TM practices and other BMPs to achieve conservation savings. | Construction/ Underway | 2022-12-01 | 2024-09-30 | Northern District/Springs Coast | SWF Heartland (excluding CFWI) |  | N/A |  |  | 0 | 0.025 | 0 | 0 | 0 | 0 | FY2022-23 through FY2025-26 | 34712.52 | 0 | 0 | 0 | 0 | 0 | 2.2.2.7 Conservation Rebates and Retrofits | WSD |  | FY23 | FY23 | 0 | 0 | 0 | 0 | 51000 | 0 | 51000 | 0 | 102000 |  |  | 55
| SWFWMD |  | Q308 |  | N882 | PRWC- West Polk Wellfield | Polk Regional Water Cooperative | 28.0741 | -82.9764 | Brackish Groundwater | No | Final design, permitting, and construction of a water production facility (WPF), wellfield and raw water transmission main to the WTP, concentrate disposal well(s), and finished water transmission mains. The WP preliminary design includes a 2.5 MGD reverse osmosis water production facility and transmission system to PRWC member utilities with a buildout capacity of 10 MGD. | The final design, permitting, and construction of the West Polk Wellfield's Regional Transmission System | Design | 2024-07-26 | 2045-09-30 | SWUCA Water Bodies | SWF CFWI-2 (including portion of Heartland) |  | N/A |  | Southern WUCA | 0 | 10 | 0 | 0 | 0 | 0 | FY2022-23 through FY2025-26 | 0 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 2.2.2.4 Brackish Groundwater Development | WSD |  | FY23 | FY26 | 0 | 0 | 1064308 | 1064308 | 107052000 | 0 | 120027692 | 106746896 | 228144000 |  |  | 56
| SWFWMD |  | Q309 |  | N882 | PRWC- Test Prod Well #2 West Polk Wellfield | Polk Regional Water Cooperative | 28.0741 | -82.9764 | Brackish Groundwater | No | A hydrogeologic investigation to continue evaluating the development of a brackish groundwater wellfield in the Lower Floridan aquifer in Polk County. The project includes the construction of one exploratory/production well, up to three monitor wells, and associated testing. An aquifer performance test and water quality sampling will be conducted. | Hydrogeologic investigation to continue evaluating the West Polk Wellfield that includes the construction of a exploratory/production well, up to three monitor wells, aquifer performance testing, and water quality sampling. | Design | 2025-01-01 | 2027-07-31 | SWUCA Water Bodies | SWF CFWI-2 (including portion of Heartland) |  | N/A |  | Southern WUCA | 0 | 0 | 0 | 0 | 0 | 0 | FY2022-23 through FY2025-26 | 373892.04 | 0 | 0 | 0 | 0 |  | 2.2.2.4 Brackish Groundwater Development | WSD |  | FY23 | FY23 |  |  | 1228000 | 1228000 | 1448500 |  | 1448500 |  | 4125000 |  |  | 57
| SWFWMD |  | Q311 | Linked | Q255 | Bay Laurel CCDD Water Conservation Program phase 2 | Bay Laurel CCDD | 29.107 | -82.2599 | PS and ICI Conservation | No | Make available financial incentives and services to residential and commercial customers for up to four conservation activities, including: replacing inefficient residential toilets with 1.28 gallon per flush high-efficiency toilets; replacing high volume shower heads with 2.0 gallons per minute WaterSense labeled showerheads; installation of evapotranspiration (ET) irrigation controllers; and landscape irrigation audits. | Financial incentives to residential and commercial customers for: high-efficiency toilets; WaterSense labeled showerheads; installation of evapotranspiration irrigation controllers; and landscape irrigation audits. | Construction/Underway | 2023-01-01 | 2024-12-31 | SWUCA Water Bodies | SWF Northern (excluding CFWI) |  | N/A |  |  | 0 | 0.055 | 0 | 0 | 0 | 0 | FY2022-23 through FY2025-26 | 63549.24 | 0 | 0 | 0 | 0 | 0 | 2.2.2.7 Conservation Rebates and Retrofits | WSD |  | FY23 | FY23 | 0 | 0 | 0 | 0 | 191900 | 0 | 191900 | 0 | 383800 |  |  | 58
| SWFWMD |  | Q313 | Linked | Q205 | PRMRWSA- Reg Integr Loop Sys Ph 3C | Peace River Manasota Regional Water Supply Authority | 27.338 | -82.383 | Distribution/Transmission Capacity | Yes | third-party review, design, permitting, and construction of a potable water transmission interconnection, to supply additional alternative water, including pumping and storage improvements at the existing Carlton facility. This interconnect is part of the Regional Integrated Loop System to extend the system further north from its current terminus at Clark Road (SR-72) to Fruitville Road. This segment will be approximately 8 miles long and is expected to have a max day capacity of 40 million gallons per day (MGD) to supply anticipated demand from a high growth area in Sarasota County.ons. | Design, permitting and construction of a potable water transmission interconnection to supply additional alternative water. | Underway | 2023-10-27 | 2026-12-01 | SWUCA Water Bodies | Southern |  | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 40 | FY2022-23 through FY2025-26 | 21842604.13 | 0 | 0 | 0 | 0 | 0 | 2.2.2.2 Regional Potabe Water Interconnects | WSD |  | FY23 | FY25 |  |  | 2500000 | 2500000 | 26550000 | 0 | 34800000 | 54020646.72 | 63850000 |  |  | 59
| SWFWMD |  | Q319 | Linked | L601 | Manatee County Toilet Rebate Project, Phase 15 | Manatee County | 27.4605 | -82.6274 | PS and ICI Conservation | No | Make available financial incentives to residential and commercial customers for the replacement of conventional toilets with high-efficiency toilets which use 1.28 gallons per flush or less. This project will make available rebates/credits for the replacement of approximately 1,000 high flow toilets. Also included are educational materials, program promotion, and surveys necessary to ensure the success of the program. Should actual costs be less than anticipated, the Cooperator may perform more installations/rebates as the availability of funds allow. | Make available approx. 1000 rebates to retail water customers for the replacement of conventional toilets with high-efficieny toilets. | Underway | 2022-10-01 | 2025-09-30 | SWUCA Water Bodies | SWF Southern |  | N/A |  |  | 0 | 0.017 | 0 | 0 | 0 | 0 | FY2022-23 through FY2025-26 | 34376.65 | 0 | 0 | 0 | 0 | 0 | 2.2.2.7 Conservation Rebates and Retrofits | WSD | 0 | FY23 | FY23 |  | 0 | 0 | 0 | 50000 | 0 | 50000 | 0 | 100000 |  |  | 60
| SWFWMD |  | Q324 |  |  | WRWSA Regional Water Supply Plan 2024 Update | Withlacoochee Regional Water Supply Authority | 28.822 | -82.493 | Other Project Type | No | This project will update the Regional Water Supply Plan (Plan) of the Withlacoochee Regional Water Supply Authority. The Plan will provide updated population and demand projections, and an evaluation of potential water supply project options and costs, including assessment of the availability of water sources within the cooperator's four-county service area through 2045. The findings of the Plan will be reflected within the District's 2025 Regional Water Supply Plan (RWSP). | This project will include population and demand projections, an evaluation of potential water supply project options and costs, including assessment of water sources within the cooperator's service area through 2045 as part of an update to the RWSP. | Underway | 2023-01-01 | 2024-09-30 | Northern District/Springs Coast | SWF Heartland (excluding CFWI) |  | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | FY2022-23 through FY2025-26 | 103494.5 | 0 | 0 | 0 | 0 | 0 | 1.1.1 Water Supply Planning | WSD | 0 | FY23 | FY23 | 0 | 0 | 0 | 0 | 175000 | 0 | 175000 | 0 | 350000 |  |  | 61
| SWFWMD |  | Q355 | Linked | Q202 | Regional Integrated Loop System, Phase 2B | Peace River Manasota Regional Water Supply Authority | 27.017 | -82.225 | Distribution/Transmission Capacity | No | This interconnect is part of the Regional Integrated Loop System to extend the system further north from its current terminus at Clark Road (SR-72) to Fruitville Road. This segment will be approximately 8 miles long and is expected to have a max day capacity of 40 million gallons per day (MGD) to supply anticipated demand from a high growth area in Sarasota County. | Design, permitting and construction of a 8 mile potable water transmision system to interconnect supply of alternative water. | Underway | 2024-03-01 | 2026-06-01 | SWUCA Water Bodies | Southern |  | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 40 | FY2022-23 through FY2025-26 | 13747604.03 | 10403906 |  | 0 | 0 | 0 | 2.2.2.2 Regional Potabe Water Interconnects | WSD | 0 | FY23 | FY26 | 0 | 0 | 1500000 | 1500000 | 36150000 | 0 | 49790545 | 78368303.19 | 87440545 |  |  | 62
| SWFWMD |  | Q371 | Linked | Q267 | Polk County Irrigation System Evaluation Program, Phase 8 | Polk County | 28.011 | -81.8087 | PS and ICI Conservation | no | Make available services to customers for up to three conservation activities, including: irrigation evaluations, installation of rain sensors, and installation of WaterSense-labeled irrigation controllers and necessary components. Also included are educational materials, program promotion, program administration, and follow-up irrigation evaluations to ensure the success of the program. | Make available services to customers for up to three conservation activities, including: irrigation evaluations, installation of rain sensors, and installation of WaterSense-labeled irrigation controllers | Underway | 2023-10-01 | 2025-12-30 | SWUCA Water Bodies | SWF Heartland, CFWI |  | N/A |  |  | 0 | 0.053 | 0 | 0 | 0 | 0 | FY2023-24 through FY2025-26 | 1918 | 0 | 0 | 0 | 0 | 0 | 2.2.2.7 Conservation Rebates and Retrofits | WSD |  | FY24 | FY24 | 0 | 0 | 0 | 0 | 72500 |  | 72500 |  | 145000 |  |  | 63
| SWFWMD |  | Q387 | Linked | Q256 | St. Pete Sensible Sprinkling Program, Phase 11 | City of St Pete | 27.786 | -82.695 | PS and ICI Conservation | No | Make available approximately 300 irrigation evaluations to single family, multi-family and commercial customers. This will include program administration and evaluations with recommendations for optimizing the use of water outdoors through Florida-friendly Landscaping TM practices and other efficient irrigation best management practices. Approximately 300 rain sensor devices will be provided and installed for project participants who do not have a functioning device. Also included are educational materials, program promotion, follow-up evaluations and surveys. | Financial incentives and services to customers for residential irrigation system | Underway | TBD | TBD | NTB WUCA Water Bodies | SWF Southern |  | N/A |  | Southern SWUCA | 0 | 0.0526 | 0 | 0 | 0 | 0 | FY2023-24 through FY2025-26 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2.2.7 Conservation Rebates and Retrofits | WSD |  | FY24 | FY24 | 0 | 0 | 0 | 0 | 50000 | 0 | 50000 | 0 | 100000 |  |  | 64
| SWFWMD |  | Q414 |  | Q215 | TBW Demand Management Plan Iplementation | Tampa Bay Water | 28.0152 | -82.7401 | PS and ICI Conservation | No | Financial incentives and services for cost effective conservation activities, including but not limited to: highefficiency plumbing fixtures, cooling tower optimization equipment, Florida Water Star rebates, soil moisture sensors, evapotranspiration (ET) irrigation controllers, and other irrigation efficiency improvements. Also included is the program administrative costs to ensure the successful implementation of the program. Tampa Bay Water (TBW) member governments are collaborating with TBW to implement and oversee the project | Financial incentives and services to customers for conservation activities. Also included is program administrative costs to ensure the success of the program. | Design | TBD | TBD | NTBWUCA Water Bodies | SWF Southern |  | N/A |  |  | 0 | 0.45 | 0 | 0 | 0 | 0 | FY2025-26 | 0 | 528000 | 0 | 0 | 0 | 0 | 2.2.2.7 Conservation Rebates and Retrofits | WSD |  | FY26 | FY26 | 0 | 0 | 0 | 0 | 528000 | 0 | 528000 |  | 1056000 |  |  | 65
[44 empty] | 0 | [7 empty] | 66
[44 empty] | 0 | [7 empty] | 67
[44 empty] | 0 | [7 empty] | 68
[44 empty] | 0 | [7 empty] | 69
[44 empty] | 0 | [7 empty] | 70
[44 empty] | 0 | [7 empty] | 71
[44 empty] | 0 | [7 empty] | 72
[44 empty] | 0 | [7 empty] | 73
[44 empty] | 0 | [7 empty] | 74
[44 empty] | 0 | [7 empty] | 75
[44 empty] | 0 | [7 empty] | 76
[44 empty] | 0 | [7 empty] | 77
[44 empty] | 0 | [7 empty] | 78
[44 empty] | 0 | [7 empty] | 79
[44 empty] | 0 | [7 empty] | 80
[44 empty] | 0 | [7 empty] | 81
[44 empty] | 0 | [7 empty] | 82
[44 empty] | 0 | [7 empty] | 83
[44 empty] | 0 | [7 empty] | 84
[44 empty] | 0 | [7 empty] | 85
[44 empty] | 0 | [7 empty] | 86
[44 empty] | 0 | [7 empty] | 87
[44 empty] | 0 | [7 empty] | 88
[44 empty] | 0 | [7 empty] | 89
[44 empty] | 0 | [7 empty] | 90
[44 empty] | 0 | [7 empty] | 91
[44 empty] | 0 | [7 empty] | 92
[44 empty] | 0 | [7 empty] | 93
[44 empty] | 0 | [7 empty] | 94
[44 empty] | 0 | [7 empty] | 95
[44 empty] | 0 | [7 empty] | 96
[44 empty] | 0 | [7 empty] | 97
[44 empty] | 0 | [7 empty] | 98
[44 empty] | 0 | [7 empty] | 99
[44 empty] | 0 | [7 empty] | 100
[44 empty] | 0 | [7 empty] | 101
[44 empty] | 0 | [7 empty] | 102
[44 empty] | 0 | [7 empty] | 103
[44 empty] | 0 | [7 empty] | 104
[44 empty] | 0 | [7 empty] | 105
[44 empty] | 0 | [7 empty] | 106
[44 empty] | 0 | [7 empty] | 107
[44 empty] | 0 | [7 empty] | 108
[44 empty] | 0 | [7 empty] | 109
[44 empty] | 0 | [7 empty] | 110
[44 empty] | 0 | [7 empty] | 111
[44 empty] | 0 | [7 empty] | 112
[44 empty] | 0 | [7 empty] | 113
[44 empty] | 0 | [7 empty] | 114
[44 empty] | 0 | [7 empty] | 115
[44 empty] | 0 | [7 empty] | 116
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## WRDWP Data Input Instructions
WRDWP INSTRUCTIONS
General Identifying Information | [16 empty] | Waterbody, RWSP, and MFL Benefited | [5 empty] | Water Made Available | [5 empty] | 5-Year Water Resource Development Work Program | [8 empty] | General Funding | [11 empty] | Comments
DEP Unique ID | Water Management District | Year First Added to RWSP/RPS | District Project Number | Phased or Linked Project | Associated District Project Number | Project Name | Cooperating Entity | Lat | Long | Project Type | Land Acquisition Component | Project Description | Short Description | Project Status | Construction Beginning Date | Construction Completion Date | Waterbody Benefited | RWSP Region Supported | RWSP or RPS Year Project Last Identified | Primary MFL Supported | Ancillary MFL Supported | MFL RPS Supported, if applicable | Quantity of Water Made Available to date (MGD) | Quantity of Water Made Available upon Completion (MGD) | Reuse Flow Made Available to date (MGD) | Reuse Flow Made Available upon Project Completion (MGD) | Storage Capacity Created (MG) | Distribution / Transmission Capacity Created (MGD) | Fiscal Year Included in 5-Year WRDWP, If Applicable | Historic District Expenditures | WRDWP Current FY Funding | WRDWP Current FY+1 Funding | WRDWP Current FY+2 Funding | WRDWP Current FY+3 Funding | WRDWP Current FY+4 Funding | Budget Reference | WRD or WSD (optional) | Projected Total Funding (for RWSP/RPS Options Only) | Initial fiscal year funded | Most recent fiscal year funded | WPSP Funding | Springs Funding | Other state funding | Total State Funding | Total District Funding | Total Land Acquisition Funding by District or State | Cooperating Entity Match | Total Construction Costs | Project Total | Comments | Explanation for 5-Year WRDWP
DEP to complete. Leave blank if not assigned already. | Include WMD acronym | For RWSP projects, this should be the first year the project appeared in a RWSP. For RPS projects that do not yet appear in a RWSP, including the RPS year where the project first appeared. For projects not included in either a RWSP or RPS, state N/A. | Include the district project number. For phased projects with discrete funding, include individually. If no project number is provided, DEP will assign a mockup number to tracking purposes. | Indicate whether the project is a phase of a larger project, or linked to another project by entering "Phased" or "Linked". If not applicable, leave blank--do not enter N/A. A phased project is one in which the overarching project could not be complete or is dependent on the completion of the indiviudal components/phases (e.g. the phases of a WTP expansion). A linked project is one that is not dependent on another project component but is programmatically associated with one (e.g. toilet rebate programs or reclaimed water lines conencting to a WTP). | List the FIRST District Project number (from column D) that the project is associated with (including the first); if the project is known to be the first phase of a multi-phase project, Column D and this column should be the same District Project Number. Quantity of water and funding information should be for this phase only to ensure there is not double counting. If not applicable, leave blank--do not enter N/A. | Include the Project Name. The project name should be consistent with the RWSP, MFL RPS, and Histroric Project List, if applicable. Project name should be kept as short as possible and need not include project type, sponsor or significant description. | List all project partners and include their full name. Cities should be listed by city name first, and then noted as "city of" (e.g., Clay County; Tequesta, City of). This is necessary to ensure that the Lead Entity is clearly identifiable (e.g., "Suwannee" could be a city, county, and WMD). | Include the latitude in decimal format (Districts are also requested to provide a GIS file with vectors for all projects in which that information is available). | Include the longitude in decimal format (Districts are also requested to provide a GIS file with vectors for all projects in which that information is available). | Districts should select the one project type that most accurately characterizes the project type. Description may include information on how the project maybe secondarily characterized by another project type. Reclaimed Water (for potable offset) Reclaimed Water (for groundwater recharge) Brackish Groundwater Surface Water Surface Water Storage (e.g., reservoirs) Aquifer Storage and Recovery Stormwater Desalination Other Non-Traditional Source Groundwater Recharge (not including ASR or reclaimed water) Data Collection and Evaluation (e.g., funding spent on specific feasibility studies, etc.) Water Resource Management Programs (e.g., MFL development, well plugging and abanadonment programs, etc.) Technical Assistance (e.g., MILs) Flood Control Works (e.g., flood control structure maintenance and repair, hydrologic restoration for flood control, etc.) PS and CII Conservation Agricultural Conservation Distribution/Transmission Capacity Other Project Type | Does this project include a land acquisition component necessary to complete the project that is being purchased, in whole or in part, with District or State funds? Yes or No. | Briefly describe the project and include an explanation of how the project will include additional water available for consumptive uses. To explain how the project will include additional water for consumptive uses as required by statute, the description must include the AWS type and proposed use (e.g., reclaimed water project for residential irrigation; ASR for the City of XYZ public supply). For non-AWS projects, this could include a description of how the program or project benefits overall water supplies or natural system protection. | The short project description should have 250 characters or less, with a sentence structure of: Action verb (Implementing, Developing, etc.) a “project type” in or near this “location” for the purpose of “benefit”. | 1) RWSP or RPS Option Only 2) Design 3) Construction or, for programs, Underway 4) Cancelled 5) Complete For projects that were cancelled, but which are still considered options for the future in the RWSP/RPS, list as RWSP or RPS Option Only, not cancelled. Cancelled should ONLY be used for projects that are not feasible or which were not selected for implementation and will not move forward. | Include date in prescribed format (mm/dd/yyyy). If day is not known, use 01. For complete and construction/ underway projects, date should be the start of construction or program start. For design, date should be the anticipated start of construction (must be in the future). For cancelled projects, leave blank. For project options, either leave blank or include anticipated date if date identified in RWSP. | Include date in prescribed format (mm/dd/yyyy). If day is not known, use 01. Date should be the actual completion date of the project (for complete projects only) or the estimated completion of the project (for design, construction/ underway/project option (if available) only). For cancelled or project options (not available), leave blank. | List name of waterbody most directly benefited by the project. A district may include more than one waterbody if appropriate separated by commas, but need not include all ancillary waterbodies benefited. The most benefited waterbody must be listed first. | List RWSP area that the project supports. You may only select one planning region. If a second planning region is benefited put it in the comment field. | List the year of the RWSP (or RPS, if appliciable) in which this project was last identified. | List name of MFL waterbody most directly benefited by the project. A district may include more than one MFL waterbody if appropriate separated by commas, but need not include all ancillary MFL waterbodies benefited (those will be captured in the next column). The most benefited MFL waterbody must be listed first and, for reporting purposes, will be the waterbody for which any benefits are attributed. If not applicable, leave blank. | List name of MFL waterbody with an ancillary benefit by the project. A district may include more than one MFL waterbody if appropriate separated by commas. If not applicable, leave blank. | Select from the drop down the applicable recovery or prevention strategy the project benefits. The project need not be listed in the strategy in order to be listed here. If not applicable, leave blank | List quantity of water made available to date in MGD for the phase identified. Do not include a number here for reclaimed water potable offset projects. Should only have a value if complete or in construction. | List quantity of water that will be made available upon project completion in MGD for the phase identified. Completion here means when the project goes fully online. Do not include a number here for reclaimed water potable offset projects. | List the total actual flow for the reuse made available to date in MGD for the phase identified. Do not include total capacity made available. Do not include reclaimed water for groundwater recharge. Should only have a value if complete or in construction. | List the total projected flow for the reuse made available when the project is fully completed in MGD for the phase identified. Completion here means when the project goes fully online. Do not include total capacity made available. Do not include reclaimed water for groundwater recharge. | List all storage capacity created in million gallons. This would include ASR that does not include any distribution at this time. This may also include completion of reservoirs, etc. | List all distribution capacity created in million gallons per day that does not directly make water available. If linked to a recently funded AWS project, be sure to complete the Phased or Linked Project column. | Include the years in which you included the project in your WRDWP. This can be a range of years but it must be in the six digit year format (i.e. FYXXXX-XX, or for a range of years, use "FYXXXX-XX through FYXXXX-XX"). | Include historic expenditures for the project (this phase only). This is for previous expenditures only, not previously budgeted funding. | Include all funding that has been budgeted for this project during the applicable fiscal year, including all funding sources (i.e. district, state, federal). | Include all funding that has been budgeted for this project during the applicable fiscal year, including all funding sources (i.e. district, state, federal). | Include all funding that has been budgeted for this project during the applicable fiscal year, including all funding sources (i.e. district, state, federal). | Include all funding that has been budgeted for this project during the applicable fiscal year, including all funding sources (i.e. district, state, federal). | Include all funding that has been budgeted for this project during the applicable fiscal year, including all funding sources (i.e. district, state, federal). | Include the budget program, activity, and sub-activity for this project. For funds that have rolled over and do not appear in the most recently adopted budget, include the budget program/activity/sub-activity and an "(RO)" to indicate it is from a previous year's budget. (e.g., 1.1.1. (RO)) | Note whether this is a WRD or WSD component. This field is optional. | Include projected project costs as set forth in a RWSP or RPS. Projected Funding must be left blank for project status other than RWSP/RPS Option. | Identify the first fiscal year the district provided funding. It must be in the six digit year format (i.e. FYXXXX-XX). | Identify the most recent (which may be the last) fiscal year the district provided funding. It must be in the six digit year format (i.e. FYXXXX-XX). | Include the total funding for this project phase as of the most recent fiscal year. | Include the total funding for this project phase as of the most recent fiscal year. | Include the total funding for this project phase as of the most recent fiscal year. | AUTO POPULATED - LOCKED CELL (Sum of AD through AF) | Include the total funding for this project phase as of the most recent fiscal year. For the WRDWP, this is the "Historic District Funding" and should NOT include the current FY. | Include the total amount of District or state funding going towards land acquisition for this project phase. | Include the total funding for this project phase as of the most recent fiscal year. | This column is only required for WPSP funds. However, if construction costs are known and the district has confidence in the data point, it is recommended that construction costs be included for non-WPSP funded projects as well. When including, please include only construction costs for this project phase. | Should not include project total of all phases. Should only include project total associated with the phase in the line item and matching the funding associated with all state or district funds. Includes all project costs, including construction, planning, design, etc., that is included in district or state funding or Lead Entity match. Project total may exceed the sum of state, district, and lead entity funding. However, it must not be LESS than the sum of state, district, and lead entity funding. | Include any additional comments the District would like to in the district's discretion. | Include explanations as needed for projects that are delayed or over budget as compared to previous 5-year WRDWP submittal.
[15 empty] | Add column(s) for septic to sewer | Septic from onsite to septic | Septic to advanced treatment
BMAP APPENDIX INSTRUCTIONS
DEP Project ID | BMAP | Lead Entity | Partners | DEP Project Number | Project Name | Project Description | Project Type | District Project Number | Lat | Long | Project Status | Construction Completion Date | TN Reduction (lbs/yr) | TP Reduction (lbs/yr) | Location | Acres Treated | Fiscal Year Included in 5-Year WRDWP, If Applicable | WRDWP Current FY Funding | WRDWP Current FY+1 Funding | WRDWP Current FY+2 Funding | WRDWP Current FY+3 Funding | WRDWP Current FY+4 Funding | Budget Reference | Total State Funding | Total District Funding | Lead Entity Match | Project Total
Copy and Paste from BMAP list. If the project being implemented by the District is only one portion or phase of the total BMAP project listed in the provided spreadsheet, make necessary edits in project description to note which phase or portion of the project is being completed as part of the 5-Year WRDWP. Additionally, on the DEP Project Number, add an A, B, C, etc. For example, LC-34-A. | [7 empty] | Include any District project number necessary for internal District tracking. | Include the latitude in decimal format | Include the longitude in decimal format | 1) Planned 2) Underway 3) Completed 4) Cancelled | Include year the project, activity, or task began reducing nutrient loading. For structural projects, this is usually the year construction was complete. For ongoing activities, this is the year the project was first implemented. For projects with a Completed status, year should be the current year or a past year. For projects with a status of Planned or Underway, date should be the current year or a future year. For Cancelled projects, leave blank. | Copy and Paste from BMAP list. If the project being implemented by the District is only one portion or phase of the total BMAP project listed in the provided spreadsheet, make necessary edits in the applicable columns. TN and TP reductions and acres treated may be adjusted downward for phased projects, but should never exceed the numbers in the BMAP project list. |  |  |  | Include this Fiscal year. | [5 empty] | Include the budget program, activity, and sub-activity for this project. Also include the page number where this project is located within the budget document. | Include the total state funding, including any Springs funds. | Include the total funding for this project phase as of the most recent fiscal year. | Include the total funding for this project phase as of the most recent fiscal year. If not known, leave blank. | Should not include project total of all phases. Should only include project total associated with the phase in the line item and matching the funding associated with all state or district funds. Includes all project costs, including construction, planning, design, etc., that is included in district or state funding or Lead Entity match. Project total may exceed the sum of state, district, and lead entity funding. However, it must not be LESS than the sum of state, district, and lead entity funding.

## WP Pivot Table
Fiscal Year Included in 5-Year WRDWP, If Applicable | (All)
Project Type | Sum of Water Made Available upon Completion (MGD) Reuse and Non-Reuse | Sum of Historic District Expenditures | Sum of WRDWP Current FY Funding | Sum of Total Future Funding (Years 2-5)
(blank) | 0 |  |  | 0
Grand Total | 0 |  |  | 0

## WP MFL Pivot Table
MFL RPS Supported, if applicable | (All)
Project Type | Sum of Water Made Available upon Completion (MGD) Reuse and Non-Reuse | Sum of Historic District Expenditures | Sum of WRDWP Current FY Funding | Sum of Total Future Funding (Years 2-5)
(blank) | 0 |  |  | 0
Grand Total | 0 |  |  | 0

## Drop Down Lists (hidden)
Project Type | Project Status | 5-Year Work Program
Reclaimed Water (for potable offset) | RWSP or RPS Option Only | Yes
Reclaimed Water (for groundwater recharge or natural system restoration) | Design | No
Brackish Groundwater | Construction/Underway
Surface Water | Cancelled
Surface Water Storage | Complete
Aquifer Storage and Recovery | On Hold
Stormwater
Desalination
Other Non-Traditional Source
Groundwater Recharge
Data Collection and Evaluation
Water Resource Management Programs
Technical Assistance
Flood Control Works
Agricultural Conservation
PS and CII Conservation
Distribution/Transmission Capacity
Other Project Type
WMD | Regions | MFL RPS
NWFWMD | NWF Region I | LSFIR Recovery Strategy
SFWMD | NWF Region II | Volusia Recovery and Prevention Strategy
SJRWMD | NWF Region III | Silver Springs Prevention Strategy
SRWMD | NWF Region IV | Southern WUCA Recovery Strategy
SWFWMD | NWF Region V | Northern Tampa Bay WUCA Recovery Strategy
| NWF Region VI | Lower Hillsborough River Recovery Strategy
| NWF Region VII | Dover/Plant City WUCA Recovery Strategy
| SF Lower Kissimmee Basin | Lower Alafia River Recovery Strategy
| SF CFWI (aka Upper Kissimmee Basin) | Everglades Restoration*
SF Upper East Coast
SF Lower East Coast
SF Lower West Coast
SJR NFRWSP
SJR Central Springs East Coast
SJR CFWI
SR NFRWSP
SR District outside NFRWSP
SWF Northern (excluding CFWI)
SWF CFWI-1 (including portion of Northern)
SWF Tampa Bay
SWF Heartland (excluding CFWI)
SWF CFWI-2 (including portion of Heartland)
SWF Southern

## LISTS (hidden)
WMD LIST | WMD | WMD REGION LIST | WMD | WMD RPS LIST
NWFWMD | NWFWMD | NWF Region I | SFWMD | Everglades Restoration* (CERP)
SFWMD | NWFWMD | NWF Region II | SJRWMD | Lower Santa Fe Ichetucknee River (LSFIR)
SJRWMD | NWFWMD | NWF Region III | SJRWMD | Volusia Strategy
SRWMD | NWFWMD | NWF Region IV | SJRWMD | Silver Springs Prevention Strategy
SWFWMD | NWFWMD | NWF Region V | SRWMD | Lower Santa Fe Ichetucknee River (LSFIR)
| NWFWMD | NWF Region VI | SWFWMD | Nothern Tampa Bay WUCA Recovery Strategy
| NWFWMD | NWF Region VII | SWFWMD | Hillsborough River Strategy
| NWFWMD | NWF District-wide | SWFWMD | Southern WUCA
| SFWMD | SF Lower Kissimmee Basin | SWFWMD | Lower Alafaia River Recovery Strategy
| SFWMD | SF CFWI (aka Upper Kissimmee Basin) | SWFWMD | Dover/Plant City WUCA Recovery Strategy
| SFWMD | SF Upper East Coast
| SFWMD | SF Lower East Coast
| SFWMD | SF Lower West Coast
| SFWMD | SF District-wide
| SJRWMD | SJR NFRWSP
| SJRWMD | SJR Central Springs East Coast
| SJRWMD | SJR CFWI
| SJRWMD | SJR District-wide
| SRWMD | SR NFRWSP
| SRWMD | SR District outside NFRWSP
| SRWMD | SR District-wide
| SWFWMD | SWF Northern (excluding CFWI)
| SWFWMD | SWF CFWI-1 (including portion of Northern)
| SWFWMD | SWF Tampa Bay
| SWFWMD | SWF Heartland (excluding CFWI)
| SWFWMD | SWF CFWI-2 (including portion of Heartland)
| SWFWMD | SWF Southern
| SWFWMD | SWF District-wide

## WRDWP BMAP Appendix
DEP Project ID | BMAP | Lead Entity | Partners | DEP Project Number | Project Name | Project Description | Project Type | District Project Number | Lat | Long | Project Status | Construction Completion Date | TN Reduction (lbs/yr) | TP Reduction (lbs/yr) | Location | Acres Treated | Fiscal Year Included in 5-Year WRDWP, If Applicable | WRDWP Current FY Funding | WRDWP Current FY+1 Funding | WRDWP Current FY+2 Funding | WRDWP Current FY+3 Funding | WRDWP Current FY+4 Funding | Budget Reference | Total State Funding | Total District Funding | Lead Entity Match | Project Total
4974 | CHHO | Citrus County | DEP/ SWFWMD | CC-12 | Citrus County Old Homosassa West Septic to Sewer | This project is for the 30% design, third-party review (TPR), final design, permitting and construction of a regional wastewater collection system necessary for connection of existing septic tanks in the Old Homosassa West area of the Chassahowitzka/Homosassa Priority Focus Area (PFA). The District requires a TPR because the conceptual construction estimate was greater than $5 million. If constructed, a minimum of 95 existing septic tanks will be connected to sewer. The benefit of this water quality project, if constructed, is the reduction of pollutants loads by an estimated 907 lbs/year of total nitrogen (TN). The project is located within the PFA of the Chassahowitzka/Homosassa Springs basin management action plan (BMAP), a SWIM priority water body. | OSTDS Phase Out | WH04 | 28.8213 | -82.4924 | Design | 2026-10-01 | 907 | N/A | Inside PFA | N/A | FY2025-26 | $ - | $ - | $ - | $ - | $ - | 2.3.1.4 Springs-Water Quality | 7568600 | 1382200 | 1382200 | 10333000
5813 | Crystal River/Kings Bay springshed | Citrus County | SWFWMD | SWF-07 | Citrus County Cambridge Green Septic to Sewer | This project is for the 30% design, third-party review (TPR), final design, permitting and construction of a regional wastewater collection system necessary for connection of existing septic tanks in the Cambridge Greens area of the Crystal River/Kings Bay Priority Focus Area (PFA). The District requires a TPR because the conceptual construction estimate was greater than $5 million. If constructed, a minimum of 312 existing septic tanks will be connected to sewer. The benefit of this water quality project, if constructed, is the reduction of pollutants loads by an estimated 3,211 lbs/year of total nitrogen (TN). The project is located within the PFA of the Crystal River/Kings Bay basin management action plan (BMAP), a SWIM priority water body. | OSTDS Phase Out | W432 | 28.8213 | -82.4924 | construction | 2025-03-16 | 3211 | N/A | Inside PFA | N/A | FY2025-26 | $ - | $ - | $ - | $ - | $ - | 2.3.1.4 Springs-Water Quality | 5750000 | 1450500 | 3042500 | 10243000
4975 | Chassahowitzka/Homosassa springshed | Citrus County | SWFWMD | CC-13 | Citrus County Old Homosassa East Septic to Sewer | This project is for the design and construction of a regional wastewater collection system necessary for connection of existing residential homes in the Old Homosassa East area of the of the Homosassa-Chasshowitzka Priority Focus Area. If constructed, a minimum of 173 existing septic systems will convert to County sanitary sewer. | OSTDS Phase Out | Q134 | 28.7817 | -82.613 | Design | 2028-07-04 | 1651 | N/A | Inside PFA | N/A | FY2025-26 | $ - | $ - | $ - | $ - | $ - | 2.3.1.4 Springs-Water Quality | 13190000 | 2470800 | 2470800 | 18131600
5027 | Weeki Wachee BMAP | Hernando County | Hernando County/ SWFWMD | HC-13 | Hernando County Weeki Wachee Springshed Nitrogen Removal Stormwater Retrofits | Design, permitting and construction of stormwater BMPs to retrofit existing retention areas with denitrification cells utilizing biosorption activated media (BAM). The retention areas are within three miles of the Weeki Wachee Springs headspring. | Retention/Detention BMP Retrofit with Nutrient Reducing Media | WW05 | 28.507 | -82.549 | Underway | TBD | 657 | N/A | Hernando | 748 | FY2025-26 | $ - | $ - | $ - | $ - | $ - | 2.3.1.4 Springs-Water Quality | 0 | 1000000 | 1000000 | 2000000
6457 | KING | DEP FPS District 2 | SWFWMD/ FWC | FPS-02 | Crystal River Preserve State Park Redfish Hole Restoration | Restore an altered estuary wetland called Redfish Hole to improve circulation, flushing, and water quality of marsh and intertidal habitat. | Hydrologic Restoration | W401 | 28.8916 | -82.621 | Planned | TBD | 0 | 0 | Springshed- Outside PFA | 54.2 | FY2025-26 | $ - | 2000000 | $ - | $ - | $ - | 2.3.1.3 Restoration Initiatives | $ - | 2197601.26 | $ - | 2197601.26
| WEEK | SWFWMD | DEP/ Florida Fish and Wildlife Conservation Commission/ Florida's Adventure Coast Visitors Bureau/ Hernando County/ Hernando County Sheriff's Office | SWF-11 | Weeki Wachee Education Campaign | To educate targeted audiences about the recreational best management practices that will help protect the Weeki Wachee River and reduce ecological impacts. | Enhanced Public Education | W466 | 28.488 | -82.504 | Underway | N/A | 0 | 0 | Basinwide | NA | FY2025-26 | 10000 | 10000 | 10000 | 10000 | 10000 | 5.1.1.2 Water Resource Education | $ - | annual request | $ - | annual request
| Crystal River/Kings Bay springshed | SWFWMD | DEP/U.S.Fish and Wildlife Service Commission/Citrus County/ /Discover Crystal River | SWF-14 | Three Sisters Education Campaign | To educate targeted audiences about the recreational best management practices that will help protect Three Sisters Springs and reduce ecological impacts. | Enhanced Public Education | W466 | 28.8213 | -82.4924 | Underway | N/A | 0 | 0 | Basinwide | NA | FY2025-26 | 5000 | 5000 | 5000 | 5000 | 5000 | 5.1.1.2 Water Resource Education | $ - | annual request | $ - | annual request
6258 | WEEK | SWFWMD | None | SWF-09 | Submerged Aquatic Vegetation Mapping | Submerged aquatic vegetation mapping at designated locations within the Weeki Wachee river. | Monitoring/Data Collection | WS01 | 28.5205 | -82.5876 | Ongoing | NA | 0 | 0 | Springshed- Inside PFA | 0 | FY2025-26 | 55000 | 55000 | 55000 | 55000 | 55000 | 1.2.1.06- Biologic Data | $ - | annual request | $ - | annual request
6259 | CHHO | SWFWMD | None | SWF-13 | Submerged Aquatic Vegetation Mapping | Submerged aquatic vegetation mapping at designated locations within the Chassahowitzka River. | Monitoring/Data Collection | WS01 | 28.7165 | -82.5801 | Ongoing | NA | 0 | 0 | Chassahowitzka Springshed- Inside PFA | 0 | FY2025-26 | 55000 | 55000 | 55000 | 55000 | 55000 | 1.2.1.06- Biologic Data | $ - | annual request | $ - | annual request
6260 | CHHO | SWFWMD | None | SWF-15 | Submerged Aquatic Vegetation Mapping | Submerged aquatic vegetation mapping at designated locations within the Homosassa River. | Monitoring/Data Collection | WS01 | 28.7165 | -82.5801 | Ongoing | NA | 0 | 0 | Homosassa Springshed- Inside PFA | 0 | FY2025-26 | 55000 | 55000 | 55000 | 55000 | 55000 | 1.2.1.06- Biologic Data | $ - | annual request | $ - | annual request
6261 | KING | SWFWMD | None | SWF-10 | Submerged Aquatic Vegetation Mapping | Submerged aquatic vegetation mapping at designated locations within the bay. | Monitoring/Data Collection | WS01 | 28.8882 | -82.5983 | Ongoing | NA | 0 | 0 | Springshed- Inside PFA | 0 | FY2025-26 | 55000 | 55000 | 55000 | 55000 | 55000 | 1.2.1.06- Biologic Data | $ - | annual request | $ - | annual request
6262 | RAIN | SWFWMD | None | R132 | Submerged Aquatic Vegetation Mapping | Submerged aquatic vegetation mapping at designated locations within the river. | Monitoring/Data Collection | WS01 | 29.1019 | -82.4371 | Ongoing | NA | 0 | 0 | Rainbow Springs Basin – Inside PFA | 0 | FY2025-26 | 55000 | 55000 | 55000 | 55000 | 55000 | 1.2.1.06- Biologic Data | $ - | annual request | $ - | annual request
TBD | WEEK/ CHHO | Hernando County | Hernando County/ SWFWMD | TBD | NW Hernando Septic to Sewer Feas. Study | A feasibility study for converting septic tanks to centralized sewer in northwest Hernando County. The proposed study will estimate nutrient loading from septic tanks within the Weeki Wachee and Chassahowitzka springshedsand identify projected project costs and phasing options for the construction of a sewer collection system. | OSTDS Phase Out | Q419 | 28.6303 | -82.52 | Design | TBD | N/A | N/A | Weeki Wachee and Homosassa / Chassahowitzka Springsheds | N/A | FY2025-26 | 75000 | 0 | 0 | 0 | 0 | 2.3.1.4 Springs-Water Quality | 0 | 75000 | 75000 | 150000